## Sheet1
Req ID | Type | Requirement Description | Design | Development | Source | Priority | Status | Testing | Test Case ID | Deployment | Notes / Dependencies
REQ-1 | Epic | Project Management |  | 1.0. | Project Management | High |  |  |  |  | Top-Level Epic Covering all PM activities
REQ-6 | Story | Task Distrubution |  | 1.1. | Project Management | High |  |  |  |  | User Story: Manage and distribute tasks across project lifecycle
REQ-7 | Sub-task | Stakeholder Meeting & Requirements Gathering |  | 1.1.1 | Stakeholders&PM | High | Completed | NAN | 1502 |  | Meet stakeholders; capture and verify all requirements
REQ-8 | Sub-task | Project Planning & Scoping |  | 1.1.2 | Stakeholders&PM | High | Completed | NAN | 1503 |  | Produce scope baseline, chater, and project schedule
REQ-9 | Sub-task | Team & Resource Management |  | 1.1.3 | Project Management | High | Completed | NAN | 1504 |  | Define roles, assign resources, manage capacity
REQ-10 | Sub-task | Project Tracking & Stakeholder Reporting |  | 1.1.4 | Stakeholders&PM | High | Completed | NAN | 1505 |  | Create status reports and communicate progress to sponsor
REQ-11 | Sub-task | Budget Tracking |  | 1.1.5 | Project Management | High | Completed | NAN | 1506 |  | Track spend against fixed $270,000 budget
REQ-2 | Epic | Platform and User Account Management |  | 2.0. | Project Management | Medium | InProgress | Yet to start | 1520 |  | Top-level Epic for authentication and profile features
REQ-12 | Story | Authentication |  | 2.1. | Development team | High | Completed | InProgress | 1521 |  | User Story: System shall allow users to register and log in securely
REQ-14 | Sub-task | Develop a signup page that registers user | InProgress | 2.1.1 | Development team | Medium | InProgress | Yet to start | 1522 |  | Integrate signup flow; capture user info in DB
REQ-15 | Sub-task | Develop a login page that checks if users are valid | Yes | 2.1.2 | Development team | High | Completed | Yet to start | 1523 |  | Validate credentials; handle failed logins gracefully
REQ-13 | Story | Profile Design and Management | InProgress | 2.2. | Development team | High | InProgress | Yet to start | 1524 |  | User Story;: Users and admins shall have manageable profiles
REQ-16 | Sub-task | Implement frontend profiles for admins and users | InProgress | 2.2.1 | Development team | Medium | InProgress | Yet to start | 1525 |  | Design and build profile UI for both user roles
REQ-17 | Sub-task | implemented backend database schemas for user data storage |  | 2.2.2 | Development team | High | Yet To Start | Yet to start | 1526 |  | Secure DB scheme: no critical/high-severity bugs in production
REQ-3 | Epic | Music Player and Interactive Lyrics |  | 3.0. | Development team | Medium | Yet to start | Yet to start | 1530 |  | Top-level Epic for core music playback and lyrics features
REQ-18 | Story | Music Player Controls | InProgress | 3.1. | Development team | High | InProgress | Yet to start | 1531 |  | User Story: Users shall control music playback seamlessly
REQ-20 | Sub-task | Implement Pause, next and back button function | InProgress | 3.1.1 | Development team | High | InProgress | Yet to start | 1532 |  | Standard playback controls; symbols intuitive per assumptions
REQ-21 | Sub-task | Optimize backend so that a song doesn't take more than 5 second to load |  | 3.1.2 | Development team | High | Completed | InProgress | 1533 |  | Accptance critetria : songs load <= 3sec: uptime>98%
REQ-22 | Story | Lyrics annotation and AI integration | InProgress | 3.2. | Project Scope Baseline | High | Backlog | Yet to start | 1534 | Yet to start | User Story: Users shall annotate, highlight, and share lyrics; AI shall generate time-based genre sessions
REQ-23 | Sub-task | Build the UI for lyrics cards and highlight the favourite picks | InProgress | 3.2.1 | Development team | High | InProgress | Yet to start | 1535 | Yet to start | Lyrics display correctly and favourite highlights work properly
REQ-24 | Sub-task | Develop the sharing mechanisms for lyrics | Yet to start | 3.2.2 | Development team | Medium | Yet to start | Yet to start | 1536 | Yet to start | Users can share selected lyrics snippets successfully
REQ-25 | Sub-task | Integrate the AI and program it to generate time-based sessions based on genre | Yet to start | 3.2.3 | Development team | High | Yet to start | Yet to start | 1537 | Yet to start | AI generates playlist/sessions correctly based on genre input
REQ-4 | Epic | Admin Controls |  | 4.0. | Development team | Medium | Yet to start | Yet to start | 1540 | Yet to start | Top-level Epic for administrative dashboard and management features
REQ-26 | Story | Administrative Dashboard | Yet to start | 4.1. | Development team | High | Yet to start | Yet to start | 1541 | Yet to start | User Story: Admins shall manage users, artists, and albums from a centralised dashboard
REQ-27 | Sub-task | Build the admin dashboard UI | Yet to start | 4.1.1 | Development team | High | Yet to start | Yet to start | 1542 | Yet to start | Admin dashboard displays correctly and allows navigation between admin features
REQ-28 | Sub-task | Implement backend logic to create, edit and remove users, artists and albums | Yet to start | 4.1.2 | Development team | High | Yet to start | Yet to start | 1543 | Yet to start | Admin can successfully manage users, artists, and albums from the dashboard
REQ-5 | Epic | Testing & Publishing |  | 5.0. | Development team | High | Yet to start | Yet to start | 1550 | Yet to start | Top-level Epic covering QA, deployment, and go-live activities
REQ-29 | Story | Testing & Quality Assurance | Yet to start | 5.1. | Development team | High | Yet to start | Yet to start | 1551 | Yet to start | User Story: All major features shall be tested and pass UAT with a 95% pass rate
REQ-30 | Sub-task | Test Planning & Case Development | Yet to start | 5.1.1 | Development team | High | Yet to start | Yet to start | 1552 | Yet to start | Test plan and test cases cover all main system functions and scenarios
REQ-31 | Sub-task | Unit & Integration Testing | Yet to start | 5.1.2 | Development team | High | Yet to start | Yet to start | 1553 | Yet to start | System modules work individually and together without major errors
REQ-32 | Sub-task | System & User Acceptance Testing | Yet to start | 5.1.3 | Development team | High | Yet to start | Yet to start | 1554 | Yet to start | UAT completed with 95% pass rate on all critical and major test cases
REQ-33 | Sub-task | Performance Testing | Yet to start | 5.1.4 | Development team | Medium | Yet to start | Yet to start | 1555 | Yet to start | System meets performance benchmarks: songs load <=3 sec; uptime >=98%
REQ-34 | Story | Deployment & Launch | Yet to start | 5.2. | Development team | High | Yet to start | Yet to start | 1556 | Yet to start | User Story: The platform shall be deployed, accessible to users, and monitored post-launch
REQ-35 | Sub-task | Production Environment Setup & Configuration | Yet to start | 5.2.1 | Development team | High | Yet to start | Yet to start | 1557 | Yet to start | System runs correctly in the production environment without configuration errors
REQ-36 | Sub-task | Data Migration & Content Loading | Yet to start | 5.2.2 | Development team | High | Yet to start | Yet to start | 1558 | Yet to start | All required data successfully migrated and content accessible in the system; 500,000+ songs loaded
REQ-37 | Sub-task | User Training & Documentation | Yet to start | 5.2.3 | Development team | Low | Yet to start | Yet to start | 1559 | Yet to start | Documentation clearly explains system usage and features
REQ-38 | Sub-task | Go-Live & Post-Launch Support | Yet to start | 5.2.4 | Development team | High | Yet to start | Yet to start | 1560 | Yet to start | System live, accessible to users, and critical issues resolved quickly post-launch