Activity List

| Activity ID | Activity Name | Activity Description | Estimated Duration (Days) | Preceding Activity | Activity Owner |
| --- | --- | --- | --- | --- | --- |
| A | Stakeholder meeting & req. gathering | To move from vague ideas to a specific list of features, rules, and constraints so the team knows what to build. | 1 days |  | PM |
| B | Project Planning & Scoping | The process of defining clear objectives, deliverables, and boundaries to ensure the team knows what is included in the project and what is excluded | 2 days | A | PM |
| C | Team & Resource Management | Strategic allocation of people, skills, and equipment to tasks to optimize efficiency and ensure the right skills are in the right place at the right time | 2 days | B | PM |
| D | Project Tracking & Stakeholder Reporting | Monitoring progress against milestones and sharing concise status reports to keep stakeholders informed of achievements and risks | 1 days | C | PM |
| E | Budget tracking | The continuous process of comparing actual expenses against planned spending to ensure the projects remains financially healthy | 1 days | D | PM |
| F | Develop a signup page that registers users | Creating a straight forward interface for new user to enter credentials, ages to terms, and register a unique account | 1 days | E | Front-end team member |
| G | Develop a login page that checks if the users are valid | Building a secure form to verify user identities by checking credentials against the database and handling invalid attempts | 1 days | E | Front-end team member |
| H | Implement frontend profiles for admins and users | Implementing distinct user interfaces that display specific data and permissions based whether the logged-in person is standard user or an administrator | 2 days | G,F | Front-end team member |
| I | Implement backend database schemas for user data storage | Designing the formal blueprint for how user data is organized, including tables for emails, password, and relationships between different data entities | 1 days | G | Back-end team member |
| J | Implement pause, next and back button function | Codding the logic that allows users to interact with media playback by pushing, skipping to the next track, or returning to a previous one | 1 days | I | Front-end team member |
| K | Optimize backend so that a song doesn’t take more than 5 seconds to load | Refining server-side logic and data retrieval methods to ensure media files load efficiently, targeting a maximum wait time of 5 seconds | 3 days | J | Back-end team member |
| L | Build the UI for lyrics cards and highlight the favourite picks | Designing visual cards to display song lyrics and implementing a “favorite” feature to highlight preferred content for user | 1 days | K,H | Front-end team member |
| M | Develop the sharing mechanisms for lyrics | Developing the technical tools that enable users to share lyrics or content with others on external platforms | 1 days | L | Front-end team member |
| N | Integrate the AI and Program it to generate time-based sessions based on genre | Programming an AI engine to analyze user preferences and generate dynamic music sessions based on specific genres and timeframes | 1 days | M | Back-end team member |
| O | Build the admin dashboard UI | Building a centralized management interface for administrators to monitor system health and navigate management tools | 2 days | L | Front-end team member |
| P | Implement backend logic to create, edit and remove users, artists and albums | Implementing backend ”CRUD” functions to allow admins to manage users, artists, and albums | 5 days | N,O | Back-end team member |
| Q | Test Planning & Case Development | Outlining the strategy for testing and writing specific scenarios to verify that every feature works as intended | 2 days | P | Team testing |
| R | Unit & Integration Testing | Testing individual code components and then verifying their interaction when combined to catch bugs early | 2 days | Q | Team testing |
| S | System & User Acceptance Testing | Conducting final testing on complete system to ensure it meets requirements and getting formal approval from the end users | 2 days | R | Team testing |
| T | Performance Testing | Stress-testing the system to see how it handles high traffic and ensuring the “5-second load time” remains stable under heavy use | 2 days | S | Team testing |
| U | Production Environment Setup & Configuration | Preparing the final”live”server where the app will actually live and be accessible to the public | 1 days | T | Back-end team member |
| V | Data Migration & Content Loading | Moving existing artist, song, and user data into the live database and ensuring all media files are correctly uploaded | 1 days | U | Back-end team member |
| X | User Training & Documentation | Creating guides or videos to show admins and users how to use the app, plus technical docs for future developers | 1 days | V | Team testing |
| Z | Go-Live & Post-Launch Support | Officially launching the app to users and staying on standby to fix any immediate bugs or technical hiccups that pop up | 1 days | X | Back-end team member |