Melodify Music Player

Project Communication Management Plan

Prepared by: Nour Waleed, Hagar Aly, Ahmed Khalid

Date: May 2026  |  Budget: $270,000  |  Deadline: 1 May 2026

Keys to Good Communication - Melodify Application

1. Focus on Group and Individual Communication Needs

| Team Member / Stakeholder | Communication Approach |
| --- | --- |
| Sponsor - Marwan Moussa | Formal monthly written reports plus one monthly face-to-face review meeting. Prefers high-level summaries with budget and milestone status. Avoid technical jargon. |
| Project Manager | Daily informal Slack check-ins with team. Weekly formal Gantt and SPI report reviewed in Monday morning stand-up. |
| Backend and Frontend Developers | Short daily stand-up (15 min via Google Meet). Task updates in ProjectLibre. Prefer informal Slack for quick questions; formal email for scope or priority changes. |
| AI Integration Engineer | Bi-weekly deep-dive technical review with PM and Backend Lead. Progress tracked in shared GitHub repository. Prefers async written updates via Notion. |
| QA Lead | Weekly QA status update in Monday stand-up. Bug reports logged in shared Jira board visible to all team members. |

2. Determining the Number of Communication Channels

Team size: 8 people (PM, 2 Frontend Devs, 3 Backend Devs, 1 AI Engineer, 1 QA Lead).

Communication channels formula: n(n-1)/2 = 8 x 7 / 2 = 28 communication channels within the team.

Including sponsor Marwan Moussa (n=9): 9 x 8 / 2 = 36 total communication channels.

The PM manages the majority of these 36 channels, spending an estimated 60-70% of project time on communication activities.

3. Formal and Informal Methods for Communicating

| Type | Formal | Informal |
| --- | --- | --- |
| Methods Used | Monthly status reports, weekly Gantt chart reports, critical path reports, change request documents, formal meeting minutes, UAT sign-off form. | Daily Slack messages, WhatsApp group for quick updates, verbal stand-ups, informal feedback during code reviews. |

4. Distributing Information Effectively and On Time

- All schedule and cost reports distributed every Monday morning before 9:00 AM.

- Any change request (e.g. CR-001 for go-live extension) communicated to sponsor within 24 hours of identification.

- Technical specification changes documented in Notion and shared with all developers within the same working day.

- Short weekly stand-up meetings (15 minutes max) to report status; longer deep-dives scheduled separately when needed.

5. Setting the Stage for Communicating Bad News

| Bad News Event | How It Was Communicated |
| --- | --- |
| A14 (AI Integration) - 3-day critical path overrun at Week 10 | PM assessed full project impact before notifying sponsor: go-live shifted by 3 days, EAC increased to $290,323. PM prepared CR-001 with corrective actions (second engineer, extended hours) before the call. Sponsor notified via phone call followed by formal written CR-001 document within 24 hours. |
| R01 - AWS API access denied at Week 8 (early warning) | Risk owner (AI Engineer) flagged the trigger to PM immediately. PM held an emergency 30-minute Google Meet with tech lead and AI engineer. Escalation plan presented to sponsor in the following Monday report before the issue became a crisis. |
| Scope creep request - Sponsor requested podcast feature at Week 6 | PM acknowledged the request positively, explained impact on schedule (+3 weeks) and cost (+$22,000), and offered to add the feature to the v2.0 roadmap. Sponsor accepted deferral. Decision documented in change register and communicated to team. |

Step 1 - Plan Communication Management

1A. Stakeholder Communications Requirements

| Stakeholder | Document / Report | Format | Method | Contact Person | Frequency | Due |
| --- | --- | --- | --- | --- | --- | --- |
| Sponsor (Marwan Moussa) | Monthly Status Report + Budget Variance | PDF + Meeting | Interactive | Project Manager | Monthly | 1st of month |
| Development Team | Weekly Gantt and SPI Report | ProjectLibre export | Push (Slack) | Project Manager | Weekly | Every Monday |
| Development Team | Daily Stand-up Minutes | Verbal + Notion | Interactive | Project Manager | Daily | 9:00 AM daily |
| AI Engineer | AI Integration Progress Report | Notion + GitHub | Pull (Notion) | AI Engineer | Bi-weekly | Every 2nd Monday |
| QA Lead | Bug Report and Test Coverage Report | Jira + PDF | Pull (Jira) | QA Lead | Weekly | Every Friday |
| All Stakeholders | Change Request (CR) Documents | PDF via email | Push (email) | Project Manager | As needed | Within 24 hrs |
| All Stakeholders | Go-Live Announcement | Email + Meeting | Interactive | Project Manager | Once | 6 May 2026 |

1B. Communication Methods and Technologies

| Method Type | Tool Used | Used For | Who |
| --- | --- | --- | --- |
| Interactive | Google Meet | Daily stand-ups, sponsor monthly meetings, emergency risk escalation calls | All team + sponsor |
| Push | Slack, Email, WhatsApp | Weekly Gantt reports, CR documents, change notifications, go-live announcement | PM to Team and Sponsor |
| Pull | Notion, GitHub, Jira | AI progress notes, code commits, bug reports, test results accessed by team as needed | Team members |

1C. Escalation Procedures

| Issue Type | Escalation Path and Timeline |
| --- | --- |
| Schedule variance > 10% on critical path | Step 1: PM notified immediately by task owner. Step 2: PM assesses impact and prepares corrective action plan within 24 hours. Step 3: PM presents to sponsor at next scheduled meeting or within 48 hours if critical. |
| Cost overrun > $10,000 above baseline | Step 1: PM activates contingency reserve. Step 2: PM prepares budget impact report within 24 hours. Step 3: Formal CR submitted to sponsor for approval before any additional spend is authorised. |
| Critical risk event triggered (R01-R03) | Step 1: Risk owner notifies PM immediately via phone or Slack. Step 2: PM convenes emergency Google Meet within 2 hours. Step 3: Response plan activated and sponsor notified within 24 hours with written summary. |
| Scope change request from sponsor | Step 1: PM acknowledges request and logs it in change register. Step 2: PM assesses schedule and cost impact within 48 hours. Step 3: PM presents options to sponsor. Step 4: If approved, formal CR issued and WBS updated. |

1D. Revision Procedures

- The communications plan is reviewed at the end of each project phase (Development, Testing, Deployment).

- Any change to stakeholder contact details, report formats, or communication frequency requires PM approval and is updated in the plan within 48 hours.

- Major revisions (new stakeholder added, reporting tool changed) require sponsor sign-off.

1E. Glossary of Common Terminology

| Term | Meaning in Melodify Context |
| --- | --- |
| SPI | Schedule Performance Index: EV divided by PV. SPI below 1 means behind schedule. Reported weekly. |
| CR (Change Request) | Formal document submitted when a change to scope, schedule, or budget is required. Example: CR-001 extended go-live by 3 days. |
| WBS | Work Breakdown Structure - hierarchical breakdown of all project deliverables and activities. |
| Critical Path | Longest sequence of tasks with zero float. Any delay on the critical path delays the go-live date. |
| Go-Live | The date Melodify is publicly launched. Revised to 6 May 2026 via CR-001. |
| UAT | User Acceptance Testing - final testing phase with target 95% pass rate before go-live. |
| Contingency Reserve | $20,950 held for known risks. Drawn from when a risk event from the register occurs. |
| Management Reserve | $39,550 held for unknown risks. Requires formal CR and sponsor approval to access. |

Step 2 - Manage Communication

2A. Performance Reporting

| Report Type | Time Focus | Content | Melodify Example (Week 10) |
| --- | --- | --- | --- |
| Progress Report | Past | What has been accomplished in the reporting period. | Authentication (A06, A07), Profile (A08, A09), Music Player (A10, A11), and Lyrics UI (A12, A13) all completed. A14 (AI Integration) 80% complete. |
| Status Report | Present | Where the project stands right now. | SPI = 0.80. EAC = $290,323. A14 delayed by 3 days due to AWS API issue. CR-001 submitted. Go-live revised to 6 May 2026. R11 (new risk) added to register. |
| Forecast Report | Future | Predicted project status based on current trends. | If second engineer added to A14 and hours extended, A14 will complete by Day 81 (3 days late). Admin, testing, and deployment phases all shift by 3 days. New go-live: 6 May 2026. |

2B. Technology Used for Communication

| Tool | Purpose | Frequency |
| --- | --- | --- |
| Slack | Team daily communication, quick status updates, risk trigger alerts. | Daily |
| Google Meet | Daily 15-min stand-up, emergency escalation calls, sponsor monthly review. | Daily + monthly |
| ProjectLibre | Gantt chart and critical path reports exported and shared every Monday. | Weekly |
| Notion | AI progress notes, meeting minutes, async technical documentation. | As needed |
| GitHub | Code version control. PM monitors commit activity to assess development progress. | Continuous |
| Jira | Bug tracking and QA reports. QA lead updates after each testing cycle. | Weekly |
| Email | Formal communications: change requests, monthly reports to sponsor, go-live announcement. | As needed |

2C. Communication Scenario - Week 10 A14 Overrun (Step-by-Step)

The following shows how the PM managed communication around the A14 critical path delay:

| Day | Action | Channel | Details |
| --- | --- | --- | --- |
| Day 70 AM | Risk trigger identified | Slack (internal) | AI Engineer sends Slack message: AWS API still blocked on Day 70, no confirmation received, A14 at risk of overrun. |
| Day 70 PM | Emergency Google Meet | Google Meet | PM, Backend Lead, and AI Engineer meet for 30 min. Decision: activate Option B (third-party AI API). PM calculates critical path impact: +3 days. |
| Day 71 | CR-001 Prepared | Notion (internal) | PM drafts CR-001 covering scope of change, cost impact (EAC $290,323), corrective actions, and revised go-live date of 6 May 2026. |
| Day 71 EOD | Sponsor Notified | Phone + Email | PM calls Marwan Moussa to explain the situation verbally. CR-001 PDF sent by email within the same hour. Sponsor approves CR-001 the next morning. |
| Day 72 | Team Informed | Slack + Stand-up | PM shares revised Gantt chart via Slack. New start dates for A15-A24 communicated in Monday stand-up. Second AI engineer assigned to A14. |

Step 3 - Monitor and Control Communication

3A. Communication Monitoring Activities

| Monitoring Activity | Melodify Application |
| --- | --- |
| Weekly Stand-up Review | PM assesses whether all team members have updated their task progress in ProjectLibre. If any activity has not been updated, PM follows up individually via Slack before end of day Monday. |
| Monthly Communication Audit | PM reviews whether all stakeholder deliverables (monthly report, Gantt, critical path report) were sent on time and acknowledged. Any missed communication is logged and corrected. |
| Sponsor Feedback - Monthly Meeting | At the start of each monthly meeting, sponsor rates communication quality on a 1-5 scale. A score below 3 triggers a communication plan revision to adjust format, frequency, or content. |
| External Communication Facilitator | At the end of the testing phase (Week 14), an external facilitator (MIU project supervisor) assesses communication effectiveness across the team and provides a short written report to the PM. |

3B. Communication Issues Identified and Actions Taken

| Week | Communication Issue | Impact | Corrective Action |
| --- | --- | --- | --- |
| 6 | AI Engineer not updating Notion notes regularly. PM unaware of integration challenges until team meeting. | PM had incomplete picture of A14 risk for 2 weeks. | Agreed to bi-weekly dedicated AI progress check-in via Google Meet. AI Engineer to post a brief async update on Notion every Friday. |
| 8 | Monthly status report to sponsor was 3 days late due to PM focus on AWS escalation. | Sponsor expressed dissatisfaction. Minor trust impact. | PM apologised and committed to never missing the 1st-of-month deadline. Designated a team member to prepare the report draft by the 28th of each month. |
| 10 | A14 delay communicated to team 2 days after PM was aware, causing confusion about revised task start dates. | Backend team started A15 prep based on old schedule, wasting 0.5 days. | PM revised protocol: any critical path change must be communicated to the full team within 4 hours of identification via Slack, even before sponsor notification. |

3C. Suggestions for Improving Project Communications

- All team members to keep ProjectLibre task completion percentage updated every Friday before 5:00 PM so Monday Gantt reports reflect accurate current data.

- PM to use a standardised weekly report template covering SPI, open risks, completed tasks, upcoming tasks, and issues to ensure consistent and complete information.

- For the remaining 4 weeks, PM to hold a 30-minute lessons-learned check-in every 2 weeks to identify communication gaps before they become issues.

- Jira bug board to be shared in the Monday stand-up screen-share so the full team is aware of open bugs, not just the QA lead.

Communication Management Summary - Melodify

| Area | Melodify Outcome |
| --- | --- |
| Keys to Communication | 36 communication channels managed. Individual profiles defined for each stakeholder. Bad news communicated proactively for A14 delay, R01 escalation, and scope change request. |
| 1. Plan | Full stakeholder communications table, method matrix (Interactive/Push/Pull), escalation procedures, revision procedures, and glossary produced. |
| 2. Manage | Progress, Status, and Forecast reports all produced at Week 10. Step-by-step CR-001 communication scenario documented. All 3 method types applied per stakeholder. |
| 3. Monitor and Control | 3 communication issues identified and resolved at Weeks 6, 8, and 10. External facilitator review planned for Week 14. Critical path change protocol updated to 4-hour notification. |