Melodify Music Player

Project Cost Management Plan

Prepared by: Nour Waleed, Hagar Aly, Ahmed Khalid

Date: May 2026  |  Budget: $270,000  |  Deadline: 1 May 2026

Step 1 — Plan Cost Management

| Component | Melodify Decision |
| --- | --- |
| Level of Accuracy | Cost estimates must be within ±10% of actual cost. |
| Units of Measure | All costs in US Dollars (USD); labor tracked in person-hours. |
| Organizational Procedure Links | Each WBS activity assigned a cost code: DEV-001 (Development), PM-001 (Project Management), QA-001 (Testing), DEP-001 (Deployment). |
| Control Thresholds | Any phase that exceeds 10% of its planned cost triggers an immediate management review. Project-level threshold: $27,000. |
| Rules of Performance Measurement | EVM metrics (CPI, SPI, EAC, TCPI) calculated and reviewed every month by the project manager. |
| Reporting Formats | Monthly budget variance reports submitted to sponsor Marwan Moussa at each stakeholder review meeting. |
| Process Descriptions | Costs estimated using bottom-up WBS approach, approved by PM, tracked monthly, and re-baselined only upon formal change request approval. |

Step 2 — Estimate Costs

2A. Cost Estimates Across Project Lifecycle

| Estimate Type | When | Range | Melodify Figure |
| --- | --- | --- | --- |
| Rough Order of Magnitude (ROM) | Project initiation (Aug 2025) | −50% to +100% | ~$250,000 — could range $125,000 to $500,000 |
| Budgetary Estimate | Planning phase (Oct 2025) | −10% to +25% | $270,000 — could range $243,000 to $337,500 |
| Definitive Estimate | Scope locked (Jan 2026) | −5% to +10% | $270,000 locked as fixed budget ±10% |

2B. FTE Staffing & Labor Cost by Phase

Developer monthly rate: $4,000 | Cloud servers/month: $500 | Tools (one-off): $2,000

| Role | Mo 1–2 | Mo 3–4 | Mo 5–6 | Mo 7–8 | Total FTE | Labor Cost (USD) |
| --- | --- | --- | --- | --- | --- | --- |
| Frontend Developer | 2.0 | 2.0 | 1.0 | 0.5 | 5.5 FTE | $22,000 |
| Backend Developer | 2.0 | 3.0 | 2.0 | 1.0 | 8.0 FTE | $32,000 |
| AI Integration Engineer | 0.0 | 1.0 | 2.0 | 1.0 | 4.0 FTE | $16,000 |
| QA / Tester | 0.5 | 0.5 | 1.0 | 2.0 | 4.0 FTE | $16,000 |
| Project Manager | 1.0 | 1.0 | 1.0 | 1.0 | 4.0 FTE | $16,000 |
| TOTAL | 5.5 | 7.5 | 7.0 | 5.5 | 25.5 FTE | $102,000 |

2C. Estimation Techniques Applied

| Technique | How It Was Applied to Melodify |
| --- | --- |
| Analogous (Top-Down) | Compared against similar music-streaming start-up projects to anchor the initial ROM at ~$250,000. |
| Bottom-Up | All 8 WBS work packages estimated individually and summed to reach the final budget of $270,000. |
| Parametric | Developer rate: $4,000/month. Backend team of 3 developers × 6 active months = $72,000. |
| Three-Point (PERT) | AI Integration: Optimistic $30,000, Most Likely $45,000, Pessimistic $70,000 → PERT Average = $47,500. |

Step 3 — Determine the Budget

3A. WBS Cost Breakdown

| WBS | Work Package | Estimate (USD) | Contingency 10% | Subtotal (USD) |
| --- | --- | --- | --- | --- |
| 1.0 | Project Management | $18,000 | $1,800 | $19,800 |
| 2.1 | Authentication (Sign-up & Login) | $22,000 | $2,200 | $24,200 |
| 2.2 | Profile Design & Management | $19,000 | $1,900 | $20,900 |
| 3.1 | Music Player Controls | $35,000 | $3,500 | $38,500 |
| 3.2 | Lyrics Annotation & AI Integration | $47,500 | $4,750 | $52,250 |
| 4.1 | Admin Dashboard | $26,000 | $2,600 | $28,600 |
| 5.1 | Testing & Quality Assurance | $24,000 | $2,400 | $26,400 |
| 5.2 | Deployment & Launch | $18,000 | $1,800 | $19,800 |
| TOTAL |  | $209,500 | $20,950 | $230,450 |

3B. Cost Baseline & Fixed Budget

| Item | Amount (USD) |
| --- | --- |
| Sum of All Work Package Estimates | $209,500 |
| Contingency Reserve (10% — known risks) | $20,950 |
| COST BASELINE | $230,450 |
| Management Reserve (unknown risks) | $39,550 |
| TOTAL FIXED PROJECT BUDGET | $270,000 |

Step 4 — Control Costs (Earned Value Management)

4A. Month 6 Status — EVM Inputs

| BAC (Fixed Budget) | PV (75% planned) | EV (60% complete) | AC (Actual Spent) |
| --- | --- | --- | --- |
| $270,000 | $202,500 | $162,000 | $175,000 |

4B. EVM Performance Metrics

| Metric | Calculation | Result | Status |
| --- | --- | --- | --- |
| CV (Cost Variance) | $162,000 − $175,000 | $-13,000 | Over budget by $13,000 |
| SV (Schedule Variance) | $162,000 − $202,500 | $-40,500 | Behind schedule by $40,500 |
| CPI | $162,000 ÷ $175,000 | 0.93 | < 1 — Getting less value per dollar spent |
| SPI | $162,000 ÷ $202,500 | 0.80 | < 1 — Only 80% of planned work completed |
| EAC | $270,000 ÷ 0.93 | $291,667 | Project will overrun fixed budget by $21,667 |
| TCPI | ($270,000 − $162,000) ÷ ($270,000 − $175,000) | 1.14 | > 1 — Must spend more efficiently for the rest of the project |

4C. Corrective Actions

- Urgent cost review of WBS 3.2 (Lyrics & AI Integration — $47,500) and WBS 3.1 (Music Player Controls — $35,000), the two largest cost drivers.

- Reduce scope of WBS 5.2.3 (User Training & Documentation) to recover ~$8,000 without impacting core delivery.

- Accelerate development velocity to close the $40,500 schedule variance before the 1 May 2026 deadline.

- Present revised EVM report to sponsor Marwan Moussa at the next stakeholder review with a corrective action plan.

- Activate Management Reserve ($39,550) only if total forecasted spend (EAC = $291,667) is formally approved via change request.