Critical Path Analysis

The critical path is the longest sequence of dependent activities. Any delay on the critical path delays the project end date. Total project duration: 111 working days (~22 weeks).

Critical path sequence: A01 → M01 → A02 → A03 → A05 → A07 → M02 → A08 → A09 → A10 → A11 → M03 → A14 → M04 → A15 → A16 → A17 → A18 → A19 → A20 → M05 → A21 → A22 → A24 → M06

| ID | Activity | ES | EF | LS | LF | Float | Dur (d) | Critical |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A01 | Stakeholder Meeting & Requirements | Day 1 | Day 8 | Day 1 | Day 8 | 0 | 7 | YES ✓ |
| M01 | Requirements Approved ♦ | Day 8 | Day 8 | Day 8 | Day 8 | 0 | 0 | YES ✓ |
| A02 | Project Planning & Scoping | Day 8 | Day 16 | Day 8 | Day 16 | 0 | 8 | YES ✓ |
| A03 | Team & Resource Management | Day 16 | Day 26 | Day 16 | Day 26 | 0 | 10 | YES ✓ |
| A04 | Budget Tracking Setup | Day 16 | Day 19 | Day 23 | Day 26 | 7 | 3 | No |
| A05 | Backend DB Schema | Day 26 | Day 31 | Day 26 | Day 31 | 0 | 5 | YES ✓ |
| A06 | Develop Sign-up Page | Day 31 | Day 36 | Day 32 | Day 37 | 1 | 5 | No |
| A07 | Develop Login Page | Day 31 | Day 37 | Day 31 | Day 37 | 0 | 6 | YES ✓ |
| M02 | Authentication Module Complete ♦ | Day 37 | Day 37 | Day 37 | Day 37 | 0 | 0 | YES ✓ |
| A08 | Frontend Profiles | Day 37 | Day 42 | Day 37 | Day 42 | 0 | 5 | YES ✓ |
| A09 | Profile Management Backend | Day 42 | Day 47 | Day 42 | Day 47 | 0 | 5 | YES ✓ |
| A10 | Music Player UI Controls | Day 47 | Day 58 | Day 47 | Day 58 | 0 | 11 | YES ✓ |
| A11 | Backend Audio Optimisation | Day 58 | Day 66 | Day 58 | Day 66 | 0 | 8 | YES ✓ |
| M03 | Music Player Functional ♦ | Day 66 | Day 66 | Day 66 | Day 66 | 0 | 0 | YES ✓ |
| A12 | Lyrics Cards UI | Day 66 | Day 70 | Day 68 | Day 72 | 2 | 4 | No |
| A13 | Lyrics Sharing Mechanism | Day 70 | Day 75 | Day 72 | Day 77 | 2 | 5 | No |
| A14 | AI Session Generator | Day 66 | Day 78 | Day 66 | Day 78 | 0 | 12 | YES ✓ |
| M04 | AI Integration Complete ♦ | Day 78 | Day 78 | Day 78 | Day 78 | 0 | 0 | YES ✓ |
| A15 | Admin Dashboard UI | Day 78 | Day 83 | Day 78 | Day 83 | 0 | 5 | YES ✓ |
| A16 | Admin Backend CRUD | Day 83 | Day 86 | Day 83 | Day 86 | 0 | 3 | YES ✓ |
| A17 | Test Planning & Case Development | Day 86 | Day 92 | Day 86 | Day 92 | 0 | 6 | YES ✓ |
| A18 | Unit & Integration Testing | Day 92 | Day 96 | Day 92 | Day 96 | 0 | 4 | YES ✓ |
| A19 | System & UAT | Day 96 | Day 100 | Day 96 | Day 100 | 0 | 4 | YES ✓ |
| A20 | Performance Testing | Day 100 | Day 103 | Day 100 | Day 103 | 0 | 3 | YES ✓ |
| M05 | UAT Sign-Off ♦ | Day 103 | Day 103 | Day 103 | Day 103 | 0 | 0 | YES ✓ |
| A21 | Production Environment Setup | Day 103 | Day 106 | Day 103 | Day 106 | 0 | 3 | YES ✓ |
| A22 | Data Migration & Content Loading | Day 106 | Day 110 | Day 106 | Day 110 | 0 | 4 | YES ✓ |
| A23 | User Training & Documentation | Day 106 | Day 107 | Day 109 | Day 110 | 3 | 1 | No |
| A24 | Go-Live & Post-Launch Support | Day 110 | Day 111 | Day 110 | Day 111 | 0 | 1 | YES ✓ |
| M06 | System Go-Live ♦ | Day 111 | Day 111 | Day 111 | Day 111 | 0 | 0 | YES ✓ |