Melodify Music Player

Project Resource Management Plan

Prepared by: Nour Waleed, Hagar Aly, Ahmed Khalid

Date: May 2026  |  Budget: $270,000  |  Deadline: 1 May 2026

Step 1 — Plan Resource Management

The resource management plan defines how human and physical resources are identified, acquired, managed, and released throughout the Melodify project lifecycle.

| Component | Melodify Decision |
| --- | --- |
| Roles and Responsibilities | Each team member has a clearly defined role. The PM owns the overall resource plan. Technical leads manage their sub-teams. The RACI chart documents accountability for all WBS activities. |
| Project Organisational Chart | Hierarchical: Sponsor (Marwan Moussa) at top, Project Manager reporting to sponsor, then Backend Lead, Frontend Lead, AI Engineer, and QA Lead as direct reports to PM. Each lead manages their sub-team members. |
| Resource Acquisition | All core team members pre-assigned at project start. Freelance resources (if needed for risk R03) sourced from Upwork within 48 hours of trigger. Physical resources (cloud servers, tools) procured in Month 1. |
| Training | AI Engineer completes a 2-day TensorFlow/HuggingFace workshop in Week 1. Backend developers complete a 1-day AWS S3 and EC2 orientation in Week 2. All team members complete a 1-hour ProjectLibre tool training in Week 1. |
| Team Development | Weekly 15-minute stand-ups build team cohesion. Monthly informal team lunch to maintain morale. PM conducts individual 1:1 check-ins every 2 weeks to address blockers and performance. |
| Resource Control | Resource utilisation tracked weekly in ProjectLibre. If any team member exceeds 100% allocation for more than 1 week, PM re-assigns tasks or extends timeline for non-critical activities. |
| Recognition and Rewards | Team members who complete critical-path activities on time and within quality standards receive a formal acknowledgement in the monthly sponsor report. Exceptional performance noted in end-of-project appraisal. |
| Regulations and Policies | All team members sign an NDA covering Melodify source code and user data. Working hours: 8 AM to 5 PM, 5 days per week. Overtime requires PM approval and is compensated at 1.5x rate from contingency reserve. |

Step 2 — Estimate Activity Resources

Resource estimates define the type and quantity of people, equipment, and materials needed for each WBS activity. The following table covers all 24 Melodify activities.

| ID | Activity | Human Resources | No. of People | Physical Resources | Tools / Software | Est. Hours | WBS Phase |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A01 | Stakeholder Meeting and Requirements Gathering | PM + Sponsor | 2 | Meeting room | Google Meet, Notion | 50 | PM |
| A02 | Project Planning and Scoping | PM | 1 | -- | ProjectLibre, Notion | 60 | PM |
| A03 | Team and Resource Management | PM | 1 | -- | ProjectLibre | 70 | PM |
| A04 | Budget Tracking Setup | PM | 1 | -- | Excel, ProjectLibre | 24 | PM |
| A05 | Backend DB Schema - User Data | Backend Lead | 1 | AWS RDS | MySQL, GitHub | 40 | 2.1 |
| A06 | Develop Sign-up Page | Frontend Dev + Backend Dev | 2 | Dev laptops | React, Node.js, GitHub | 80 | 2.1 |
| A07 | Develop Login Page | Frontend Dev + Backend Dev | 2 | Dev laptops | React, Node.js, GitHub | 96 | 2.1 |
| A08 | Frontend Profiles - Admins and Users | 2 x Frontend Devs | 2 | Dev laptops | React, Figma, GitHub | 80 | 2.2 |
| A09 | Profile Management Backend | 2 x Backend Devs | 2 | AWS EC2 | Node.js, MySQL, GitHub | 80 | 2.2 |
| A10 | Music Player UI Controls | 2 x Frontend Devs | 2 | Dev laptops | React, Web Audio API, GitHub | 160 | 3.1 |
| A11 | Backend Audio Optimisation | 2 x Backend Devs | 2 | AWS EC2, S3, CloudFront CDN | Node.js, ffmpeg, GitHub | 120 | 3.1 |
| A12 | Lyrics Cards UI | Frontend Dev | 1 | Dev laptop | React, Figma, GitHub | 64 | 3.2 |
| A13 | Lyrics Sharing Mechanism | Frontend Dev + Backend Dev | 2 | Dev laptops | React, Node.js, GitHub | 72 | 3.2 |
| A14 | AI Session Generator Integration | AI Engineer + Backend Dev | 2 | AWS EC2 (GPU tier), S3 | Python, TensorFlow, HuggingFace, GitHub | 160 | 3.2 |
| A15 | Admin Dashboard UI | Frontend Dev | 1 | Dev laptop | React, Figma, GitHub | 80 | 4.1 |
| A16 | Admin Backend CRUD | Backend Dev | 1 | AWS EC2 | Node.js, MySQL, GitHub | 48 | 4.1 |
| A17 | Test Planning and Case Development | QA Lead + PM | 2 | -- | Jira, Excel | 48 | 5.1 |
| A18 | Unit and Integration Testing | QA Lead + 1 Developer | 2 | Test environment (AWS) | Jest, Postman, Jira | 64 | 5.1 |
| A19 | System and User Acceptance Testing | QA Lead + 2 Developers | 3 | Staging environment (AWS) | Selenium, Jira, Notion | 56 | 5.1 |
| A20 | Performance Testing | QA Lead + Backend Lead | 2 | AWS EC2 load test env | JMeter, Jira | 24 | 5.1 |
| A21 | Production Environment Setup | Backend Lead + DevOps (Backend Dev) | 2 | AWS EC2, RDS, S3, CloudFront | AWS Console, Terraform | 24 | 5.2 |
| A22 | Data Migration and Content Loading | Backend Dev + AI Engineer | 2 | AWS S3, RDS | Python scripts, AWS CLI | 56 | 5.2 |
| A23 | User Training and Documentation | PM + Frontend Dev | 2 | -- | Notion, Canva | 8 | 5.2 |
| A24 | Go-Live and Post-Launch Support | Full team | 8 | Production AWS environment | AWS CloudWatch, Slack, Jira | 8 | 5.2 |
| TOTAL | 24 Activities |  |  |  |  | 1,513 hrs |  |

Step 3 — Acquire Resources

3A. Human Resource Acquisition

| ID | Role | Name | Type | Start Date | FTE | Acquisition Method |
| --- | --- | --- | --- | --- | --- | --- |
| HR-01 | Project Manager | Nour Waleed | Internal | 1 Sep 2025 | 1.0 | Pre-assigned at project charter sign-off. |
| HR-02 | Backend Lead Developer | Ahmed Khalid | Internal | 1 Sep 2025 | 1.0 | Pre-assigned. Primary owner of DB schema, audio optimisation, and admin backend. |
| HR-03 | Backend Developer 1 | Youssef Samir | Internal | 1 Sep 2025 | 1.0 | Pre-assigned. Supports login, profile backend, and data migration. |
| HR-04 | Backend Developer 2 | Layla Hassan | Internal | 1 Sep 2025 | 1.0 | Pre-assigned. Supports A14 AI integration and production environment setup. |
| HR-05 | Frontend Developer 1 | Hagar Aly | Internal | 1 Sep 2025 | 1.0 | Pre-assigned. Leads player UI controls, profile UI, and admin dashboard. |
| HR-06 | Frontend Developer 2 | Malak Tarek | Internal | 1 Sep 2025 | 1.0 | Pre-assigned. Leads sign-up and login pages, lyrics cards, and documentation. |
| HR-07 | AI Integration Engineer | Omar Fathy | Internal | 1 Nov 2025 | 1.0 | Joins project at Month 3 when AI integration work begins (A14). Pre-assigned. |
| HR-08 | QA Lead | Sara Mostafa | Internal | 1 Sep 2025 | 0.5 | Pre-assigned at 50% capacity in Months 1-6, full-time from Month 7 for testing phase. |
| HR-09 | Freelance Developer (contingency) | TBD - Upwork | External | On trigger (Risk R03) | 1.0 | Activated only if a core developer is absent for more than 3 consecutive working days. Sourced from Upwork within 48 hours at $50/hour. |

3B. Physical Resource Acquisition

| Resource | Type | Supplier / Platform | Quantity | Monthly Cost | Notes |
| --- | --- | --- | --- | --- | --- |
| Developer Laptops | Hardware | Existing team equipment | 7 | $0 | All core team members own their laptops. Spec: min 16GB RAM, i7 processor. |
| AWS EC2 Instances | Cloud Compute | Amazon Web Services | 3 instances | $200/month | 2 x t3.medium (dev/staging) + 1 x m5.large (production). Costs tracked against budget item DEP-001. |
| AWS S3 Storage | Cloud Storage | Amazon Web Services | 1 bucket (5TB) | $115/month | Stores 500,000+ audio files. S3 Intelligent-Tiering activated to optimise cost (Risk R09 mitigation). |
| AWS RDS (MySQL) | Cloud Database | Amazon Web Services | 1 instance | $80/month | db.t3.medium instance for user data, music metadata, and admin records. |
| AWS CloudFront CDN | Content Delivery | Amazon Web Services | 1 distribution | $55/month | Reduces audio load time to meet the 3-second SLA. Critical for Risk R05 mitigation. |
| GitHub Teams | Version Control | GitHub | 1 organisation | $32/month | Source code repository for all frontend, backend, and AI modules. All 8 developers have access. |
| Jira Software | Project Tracking | Atlassian | 1 workspace | $28/month | Bug tracking, QA test runs, and sprint board. QA Lead is the primary admin. |
| Figma (Professional) | UI Design Tool | Figma Inc. | 2 seats | $30/month | Used by both frontend developers for UI mockups and design handoff. |
| ProjectLibre | Schedule Tool | Open source | 8 licences | $0 | Free open-source tool. All team members trained in Week 1. |
| Notion | Documentation | Notion Labs | 1 workspace | $16/month | Project documentation, AI progress notes, meeting minutes, and risk register. |
| TOTAL MONTHLY INFRASTRUCTURE COST |  |  |  | $556/month | Total across 8 months: $4,448. Within the $18,000 Project Management WBS budget item. |

Step 4 — Develop the Team

4A. Training Plan

| Training | Content | Who Attends | When | Duration | Outcome |
| --- | --- | --- | --- | --- | --- |
| TensorFlow / HuggingFace Workshop | Training AI models for genre-based music session generation. Covers model selection, fine-tuning, and evaluation metrics. | AI Engineer (HR-07) + Backend Lead (HR-02) | Week 1 (Sep 2025) | 2 days | AI Engineer able to begin A14 integration independently by Week 9. |
| AWS S3, EC2 and CloudFront Orientation | Setting up storage buckets, EC2 instances, and CDN distribution. Focus on audio streaming optimisation. | Both Backend Devs (HR-03, HR-04) + Backend Lead (HR-02) | Week 2 (Sep 2025) | 1 day | Backend team able to configure AWS infrastructure for A11 and A21 independently. |
| ProjectLibre Tool Training | How to log task progress, update % complete, and read critical path and Gantt reports. | All 8 team members | Week 1 (Sep 2025) | 1 hour | All team members update ProjectLibre correctly every Friday, enabling accurate Monday reports. |
| Security and GDPR Briefing | HTTPS setup, bcrypt password hashing, data encryption at rest, and GDPR compliance requirements for user data. | Backend Lead (HR-02) + Both Backend Devs (HR-03, HR-04) | Week 3 (Sep 2025) | 3 hours | Security standards applied from A05 onwards. Risk R07 (GDPR) probability reduced from Low to Very Low. |
| Jest and Postman Testing | Unit testing with Jest, API testing with Postman, and writing test cases for all Melodify API endpoints. | QA Lead (HR-08) + 2 Developers | Week 8 (Nov 2025) | 1 day | QA team ready to execute A18 (Unit and Integration Testing) with full toolchain coverage. |

4B. Team Ground Rules

| Rule | Detail |
| --- | --- |
| Daily stand-up attendance | All team members must join the 9:00 AM daily Google Meet stand-up or send a written update on Slack before 9:00 AM if unable to attend. |
| ProjectLibre updates | Every team member must update their task completion percentage in ProjectLibre every Friday before 5:00 PM. Failure to update triggers a Slack reminder from the PM. |
| Code commit standards | All code must be committed to GitHub with a descriptive commit message referencing the activity ID (e.g., A11: audio compression added). No direct commits to main branch - all changes via pull request. |
| Issue escalation | Any blocker that will impact a task by more than 1 day must be escalated to the PM within 4 hours of identification via Slack direct message, not the group channel. |
| Meeting punctuality | Stand-ups start at 9:00 AM sharp and end by 9:15 AM. Monthly sponsor reviews start at 10:00 AM and are capped at 60 minutes. PM sends agenda 24 hours in advance. |
| Confidentiality | All Melodify source code, user data, and business logic are confidential. No sharing outside the team without PM approval. NDA signed by all team members at project start. |

4C. Team Performance Assessment

| Assessment Method | Frequency | Conducted By | Outcome |
| --- | --- | --- | --- |
| Task completion rate vs. PERT estimate | Weekly (every Monday) | PM reviewing ProjectLibre | Identifies team members consistently behind schedule for early intervention. |
| 1:1 check-in | Every 2 weeks | PM with each team member | Addresses individual blockers, workload issues, and morale. PM adjusts task allocation if needed. |
| Code review quality | Per pull request | Tech Lead (Backend or Frontend) | Ensures code meets Melodify quality standards before merging. Defect rate tracked monthly. |
| End-of-phase retrospective | End of each phase | PM with full team | What went well, what to improve, and action items for the next phase. Results shared with sponsor. |

Step 5 — Manage the Team

5A. RACI Chart — Key Melodify Activities

R = Responsible (does the work)  |  A = Accountable (owns the outcome)  |  C = Consulted (provides input)  |  I = Informed (kept in the loop)

| Activity / Deliverable | PM | Backend Lead | Backend Dev 1 | Backend Dev 2 | Frontend Dev 1 | Frontend Dev 2 | AI Engineer | QA Lead |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements Gathering (A01) | A | C | I | I | C | C | I | I |
| Project Planning and Scoping (A02) | R/A | C | I | I | I | I | I | I |
| Backend DB Schema (A05) | A | R | C | C | I | I | I | I |
| Sign-up and Login Pages (A06, A07) | A | C | R | I | R | I | I | C |
| Profile UI and Backend (A08, A09) | A | C | I | R | R | C | I | I |
| Music Player UI Controls (A10) | A | C | I | I | R | R | I | C |
| Backend Audio Optimisation (A11) | A | R | C | R | I | I | C | C |
| AI Session Generator (A14) | A | C | I | C | I | I | R | I |
| Admin Dashboard UI and Backend (A15, A16) | A | R | I | I | R | I | I | C |
| Test Planning (A17) | A | C | I | I | I | I | I | R |
| Unit, Integration, System and UAT (A18-A20) | A | C | R | R | R | R | C | R |
| Production Setup and Deployment (A21-A24) | R/A | R | C | R | I | I | C | R |

5B. Conflict Resolution and Team Issue Log

| Week | Issue | Parties Involved | Resolution Method | Outcome |
| --- | --- | --- | --- | --- |
| 6 | AI Engineer (HR-07) and Backend Lead (HR-02) disagreed on which AI framework to use for A14: TensorFlow vs. a lighter rule-based engine. | HR-07 (AI Engineer), HR-02 (Backend Lead) | PM facilitated a 1-hour technical decision meeting with both parties. | Decision: Use TensorFlow for better long-term scalability. Rule-based engine kept as fallback (Risk R02 contingency). Documented in Notion and added to risk register. |
| 8 | Frontend Developer 2 (HR-06) raised concern about being overloaded with 3 concurrent tasks (A12, A13, A23) while others had lighter loads. | HR-06 (Frontend Dev 2), PM | PM reviewed resource allocation in ProjectLibre. Task re-assignment. | A23 (User Training and Documentation) reassigned to HR-05 (Frontend Dev 1) who had buffer capacity. HR-06 allocation reduced to 90%. |
| 10 | A14 overrun created tension: Backend Lead felt AI Engineer should have flagged the AWS issue earlier to avoid the critical path impact. | HR-02 (Backend Lead), HR-07 (AI Engineer) | PM held a private 30-minute 1:1 with both separately, then a joint meeting. | Both acknowledged communication gap. New protocol added to comms plan: risk triggers must be Slack-messaged to PM within 4 hours. Tension resolved. CR-001 filed. |

Step 6 — Control Resources

6A. Resource Utilisation — Monthly Snapshot

Resource utilisation is tracked in ProjectLibre every week. The table below shows the planned vs. actual utilisation at the end of Month 5 (Week 10 status review).

| ID | Role | Planned Hours M1-2 | Planned Hours M3-4 | Planned Hours M5 | Actual Hours M5 | Variance (hrs) | % Util. | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| HR-01 | Project Manager | 160 | 160 | 80 | 86 | +6 | 108% | Slightly over - A14 escalation added unplanned PM hours. |
| HR-02 | Backend Lead | 160 | 240 | 80 | 80 | 0 | 100% | On track. |
| HR-03 | Backend Developer 1 | 160 | 160 | 80 | 80 | 0 | 100% | On track. |
| HR-04 | Backend Developer 2 | 160 | 200 | 80 | 96 | +16 | 120% | Overloaded - assigned to A14 support after AWS delay. PM reviewing. |
| HR-05 | Frontend Developer 1 | 160 | 160 | 80 | 76 | -4 | 95% | Slightly under - A23 reassigned from HR-06 absorbed well. |
| HR-06 | Frontend Developer 2 | 160 | 160 | 80 | 72 | -8 | 90% | A23 removed from workload. Now at healthy utilisation. |
| HR-07 | AI Engineer | N/A | 80 | 80 | 104 | +24 | 130% | Significantly overloaded due to A14 overrun and AWS workaround. Second engineer added (CR-001). |
| HR-08 | QA Lead | 40 | 40 | 40 | 40 | 0 | 100% | On track. Full-time from Month 7. |

6B. Resource Control Actions Taken

| Week | Resource Issue | Root Cause | Corrective Action |
| --- | --- | --- | --- |
| 8 | HR-06 (Frontend Dev 2) at 115% allocation. | Three tasks (A12, A13, A23) were assigned concurrently without checking total hours against available capacity in ProjectLibre. | A23 reassigned to HR-05 who had 10% spare capacity. HR-06 allocation reduced to 90%. PM added a rule: no team member to exceed 100% planned allocation without PM approval. |
| 10 | HR-07 (AI Engineer) at 130% allocation due to A14 overrun and AWS workaround. | A14 took 15 days instead of 12 due to external AWS API delay (Risk R01). HR-07 had to implement Option B (third-party AI API) while also running original A14 tasks. | Second AI engineer sourced from Upwork (HR-09 activated under Risk R03 contingency plan) at $50/hour. HR-07 returned to 100% allocation by Week 11. Additional cost of $2,400 drawn from contingency reserve. |
| 10 | HR-01 (PM) at 108% allocation. | Unplanned time spent managing CR-001, escalating R01 to sponsor, coordinating second engineer onboarding, and updating risk register simultaneously. | PM delegated sprint board updates to Backend Lead (HR-02) for Weeks 11-12. PM allocation reduced to 100% from Week 11. |

6C. Resource Histogram — Planned FTE per Phase

| Role | Mo 1 | Mo 2 | Mo 3 | Mo 4 | Mo 5 | Mo 6 | Mo 7 | Mo 8 | Total FTE-Months |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Manager | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 8.0 |
| Backend Lead | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 8.0 |
| Backend Dev 1 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 0.5 | 0.5 | 7.0 |
| Backend Dev 2 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 0.5 | 0.5 | 7.0 |
| Frontend Dev 1 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 0.5 | 0.5 | 0.5 | 6.5 |
| Frontend Dev 2 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 0.5 | 0.5 | 0.5 | 6.5 |
| AI Engineer | 0.0 | 0.0 | 1.0 | 1.0 | 1.0 | 1.0 | 0.5 | 0.5 | 5.0 |
| QA Lead | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1.0 | 1.0 | 5.0 |
| TOTAL FTE | 6.5 | 6.5 | 7.5 | 7.5 | 7.5 | 6.5 | 5.0 | 5.5 | 53.0 |

Resource Management Summary — Melodify

| Process | Melodify Outcome |
| --- | --- |
| 1. Plan | Resource management plan produced covering roles, acquisition, training, team development, recognition, and regulations. RACI and ground rules defined. |
| 2. Estimate Resources | All 24 activities fully resourced. Total 1,513 hours of effort across 8 team members. Physical infrastructure: $556/month ($4,448 total). All tool and platform requirements documented. |
| 3. Acquire Resources | 8 pre-assigned internal team members. AI Engineer joins Month 3. Freelance developer (HR-09) on standby for Risk R03. All physical and cloud resources procured in Month 1. |
| 4. Develop Team | 5 targeted training sessions completed. Ground rules established and enforced. Bi-weekly 1:1s and end-of-phase retrospectives conducted throughout project. |
| 5. Manage Team | RACI chart covers all 12 key activity groups. Three team conflicts resolved at Weeks 6, 8, and 10. New communication protocol added to comms plan following Week 10 issue. |
| 6. Control Resources | HR-04 peaked at 120% and HR-07 at 130% due to A14 overrun. Corrective actions: task redistribution, HR-09 (freelance) activated, PM delegation. All team members returned to 100% by Week 11. |