Melodify Music Player

Project Risk Management Plan

Prepared by: Nour Waleed, Hagar Aly, Ahmed Khalid

Date: May 2026  |  Budget: $270,000  |  Deadline: 1 May 2026

Melodify Risk Attitude

| Item | Melodify Position |
| --- | --- |
| Risk Attitude | Risk-Averse. Melodify has a fixed $270,000 budget and a hard go-live deadline of 1 May 2026. Zero tolerance for cost overruns. Schedule delays on the critical path are treated as critical threats. |
| Negative Risk | Threats that could delay the project or cause cost overruns: AWS API delays, AI model underperformance, key developer illness. |
| Positive Risk (Opportunity) | Early AI prototype delivery enabling additional feature testing. Discovery of AWS Activate cloud credits reducing infrastructure costs by 15%. |

Step 1 - Plan Risk Management

| Component | Melodify Decision |
| --- | --- |
| Methodology | Risk identification via team brainstorming sessions and Delphi technique with two external software consultants. SWOT analysis conducted during project initiation. Risks tracked in a Risk Register (Excel). |
| Roles and Responsibilities | Risk Owner (overall): Project Manager. Technical risks: Backend Lead and AI Engineer. Schedule risks: PM + Tech Lead. Budget risks: PM + Sponsor Marwan Moussa. Each risk in the register has an assigned owner. |
| Budget for Risk Management | Contingency Reserve: $20,950 (10% of estimates - known risks). Management Reserve: $39,550 (unknown risks). Total risk budget: $60,500. |
| Schedule for Risk Activities | Risk identification: Week 1. Qualitative analysis: Week 2. Quantitative analysis: Week 3. Risk register reviewed every 2 weeks throughout the project lifecycle. |
| Risk Categories (RBS) | Technical (AI integration, audio performance), External (AWS API, third-party licences), Organisational (team capacity, budget), Project Management (scope creep, schedule variance). |
| Probability and Impact Scale | Probability: Low (<30%), Medium (30-60%), High (>60%). Impact: Low (minor delay/cost), Medium (affects a phase), High (threatens go-live or budget cap). |
| Stakeholder Risk Tolerances | Sponsor Marwan Moussa: accepts up to 1-week schedule slip and up to $10,000 cost overrun before escalation. No tolerance for data privacy breaches or system downtime at launch. |
| Tracking and Auditing | Tracking: PM reviews risk register every 2 weeks and updates probability, impact, and status. Auditing: External risk audit conducted at end of each project phase to verify response plans are being followed. |
| Contingency Plan | Pre-defined actions activated when a risk event occurs. Example: if AWS API access is delayed, fall back to mock API for testing while procurement is resolved. |
| Fallback Plan (Plan B) | Activated when the contingency plan fails. Example: if AI model cannot be delivered on time, launch with manual genre curation and defer AI features to v1.1 post-launch. |

Risk Breakdown Structure (RBS) - Melodify

| Technical | External | Organisational | Project Management |
| --- | --- | --- | --- |
| AI model underperformance | AWS API rate-limit delay | Key developer illness/absence | Scope creep from stakeholder |
| Audio streaming latency > 3s | Third-party music licence issues | Team skill gap in AI development | Inaccurate duration estimates |
| Database schema flaws | Cloud cost exceeds budget | Budget freeze by sponsor | Poor test coverage - post-launch bugs |
| Security / data privacy breach | Regulatory compliance (GDPR) | Communication breakdown in team | Critical path delay (e.g. A14) |

Step 2 - Identify Risks

2A. SWOT Analysis - Melodify

| Strengths (Internal - Positive) | Weaknesses (Internal - Negative) |
| --- | --- |
| Experienced backend and frontend development team. Clear and approved project scope with a fixed WBS. Defined $270,000 budget with contingency and management reserves. Use of industry-standard tools: ProjectLibre, AWS, CPM scheduling. | No prior AI-powered music feature delivery experience in the team. Tight 8-month deadline with limited buffer for rework. Small team size (25.5 FTE) with limited redundancy. Early ROM estimate ($250K) was 8% below final budget, indicating estimation risk. |
| Opportunities (External - Positive) | Threats (External - Negative) |
| Growing demand for personalised music streaming. Availability of open-source AI libraries (TensorFlow, HuggingFace) reducing AI development cost. AWS Activate cloud credits could reduce hosting costs by 15%. Early AI prototype completion allows additional feature testing. | AWS API rate-limit approval delay (already occurred in A14). Third-party music licensing restrictions may limit 500,000-song library target. GDPR compliance may require additional backend security work. Competing platforms launching similar AI features during development. |

2B. Risk Register - Identification and Analysis

| No. | Rank | Risk | Description | Category | Root Cause | Trigger | Prob. | Impact | Rating | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R01 | 1 | AWS API Access Delay | AWS rate-limit approval for AI session generation API delayed, blocking A14 (AI Integration). Occurred at Week 10. | External | External vendor dependency not confirmed early enough. | AWS confirmation email not received by Week 8 | High | High | Critical | AI Engineer |
| R02 | 2 | AI Model Underperformance | AI recommendation engine fails to meet the 85% user satisfaction target for time-based genre sessions. | Technical | Insufficient training data or wrong model selection. | AI genre session accuracy below 70% in testing | Medium | High | High | AI Engineer |
| R03 | 3 | Key Developer Absence | Loss of a backend or AI developer for an extended period due to illness or emergency. | Organisational | Small team size with no redundancy on critical-path activities. | Developer absent for more than 3 consecutive working days | Medium | High | High | Project Manager |
| R04 | 4 | Scope Creep | Sponsor Marwan Moussa requests additional features (e.g. podcast support) after scope baseline is locked. | Project Mgmt | Sponsor not fully engaged in scope definition phase. | Sponsor requests features outside approved WBS | Medium | Medium | Medium | Project Manager |
| R05 | 5 | Audio Streaming Latency > 3s | Music playback fails to meet the 3-second load time SLA, failing performance testing (A20). | Technical | Unoptimised audio compression or insufficient CDN configuration. | Performance test results show average load time above 2.5s | Medium | High | High | Backend Lead |
| R06 | 6 | Music Licensing Restrictions | Third-party music rights holders restrict access to tracks, reducing library below 500,000 songs target. | External | Licensing agreements not finalised before content loading phase. | Legal team flags licensing issue during content loading (A22) | Low | High | Medium | Project Manager |
| R07 | 7 | GDPR / Data Privacy Breach | User personal data stored or transmitted without proper encryption, violating GDPR. | External | Security review not built into development sprint process. | Security audit finds unencrypted user data in DB | Low | High | Medium | Backend Lead |
| R08 | 8 | Inaccurate Duration Estimates | Activity durations significantly underestimated, causing schedule overrun across multiple phases. | Project Mgmt | Estimates made without sufficient historical data or expert review. | SPI drops below 0.85 in any two consecutive weeks | Medium | Medium | Medium | Project Manager |
| R09 | 9 | Cloud Cost Overrun | AWS infrastructure costs exceed budget due to higher-than-expected storage or compute usage. | External | Underestimation of storage needs for 500,000+ songs. | Monthly AWS bill exceeds $600 vs. planned $500 | Low | Medium | Low | Project Manager |
| R10 | 10 | Poor Test Coverage - Post-Launch Bugs | Insufficient test coverage leads to critical bugs discovered post-launch, damaging user experience. | Project Mgmt | Test planning (A17) rushed due to schedule pressure from upstream delays. | UAT pass rate below 90% at end of A19 | Medium | Medium | Medium | QA Lead |

Step 3 - Qualitative Risk Analysis

3A. Probability / Impact Matrix

| Probability / Impact | Low Impact | Medium Impact | High Impact |
| --- | --- | --- | --- |
| High (>60%) | -- | -- | R01 AWS API Delay ¦ R05 Audio Latency |
| Medium (30-60%) | -- | R04 Scope Creep ¦ R08 Estimate Errors ¦ R10 Test Coverage | R02 AI Underperformance ¦ R03 Dev Absence |
| Low (<30%) | R09 Cloud Cost Overrun | R06 Music Licensing ¦ R07 GDPR Breach | -- |

3B. Top 10 Risk Item Tracking - Melodify (Week 10 Review)

| No. | Risk | Current Rank | Previous Rank | Times on List | Status | Progress Summary |
| --- | --- | --- | --- | --- | --- | --- |
| R01 | AWS API Access Delay | 1 | 1 | 5 | Open | Occurred at Week 10. CR-001 raised. Second engineer added. Go-live extended to 6 May 2026. |
| R02 | AI Model Underperformance | 2 | 3 | 4 | Open | Model accuracy at 72% in Week 9 test. Additional training data sourced. Target 85% by Week 14. |
| R03 | Key Developer Absence | 3 | 2 | 5 | Open | Backend lead absent 1 day in Week 7. Tasks redistributed. No critical path impact. Monitoring ongoing. |
| R04 | Scope Creep | 4 | 4 | 3 | Open | Sponsor requested podcast feature in Week 6. Logged in change register. Deferred to v2.0 roadmap. |
| R05 | Audio Streaming Latency | 5 | 6 | 3 | Open | CDN caching implemented in A11. Latest test shows 2.8s avg load time. Monitoring continues in A20. |
| R06 | Music Licensing Restrictions | 6 | 5 | 2 | Open | Legal counsel engaged in Month 3. 420,000 tracks licenced so far. 80,000 remaining. On track for go-live. |
| R07 | GDPR / Data Privacy | 7 | 7 | 2 | Monitoring | HTTPS and bcrypt implemented in A05. Security audit passed in A09. No issues found. Ongoing monitoring. |
| R08 | Inaccurate Duration Estimates | 8 | 8 | 4 | Open | A11 ran 1 day over PERT estimate. Recovered via non-critical task re-sequencing. PERT review at Week 12. |
| R09 | Cloud Cost Overrun | 9 | 10 | 2 | Closed | S3 Intelligent-Tiering activated in Month 2. Current monthly AWS bill: $480. Within budget. Risk closed. |
| R10 | Test Coverage / Post-Launch Bugs | 10 | 9 | 3 | Open | QA sprint protected from feature additions. Test plan covers 100% of WBS features. UAT starts Week 13. |

Step 4 - Quantitative Risk Analysis

4A. Expected Monetary Value (EMV) - Decision Tree for R01

The PM evaluated two options for the AWS API delay. EMV analysis determined the best course of action.

| Decision Option | Outcome | Probability | Cost Impact ($) | EMV ($) |
| --- | --- | --- | --- | --- |
| Option A: Wait for AWS Access | AWS approves within 1 week - no rework needed | 40% | $0 additional cost | $0 |
| Option A: Wait for AWS Access | AWS delays by 2+ weeks - critical path slip | 60% | -$18,000 (extra dev time + deadline risk) | -$10,800 |
| Option A Total EMV |  |  |  | -$10,800 |
| Option B: Third-Party AI API | Integration succeeds, meets deadline | 70% | -$4,000 (new API licence cost) | -$2,800 |
| Option B: Third-Party AI API | Integration fails - fallback to manual curation | 30% | -$8,000 (rework + manual effort) | -$2,400 |
| Option B Total EMV |  |  |  | -$5,200 |
| DECISION: Option B selected (EMV -$5,200 vs -$10,800) | Switch to third-party AI API while escalating AWS access in parallel. | - |

4B. Sensitivity Analysis - Top Cost-Impacting Risks

| No. | Risk | Best Case | Most Likely | Worst Case | Effect on $270,000 Budget |
| --- | --- | --- | --- | --- | --- |
| R01 | AWS API Delay | $0 | $10,800 | $18,000 | Worst case = 6.7% of budget. Covered by contingency reserve. |
| R02 | AI Underperformance | $0 | $6,000 | $15,000 | Worst case = 5.6% of budget. Covered by contingency reserve. |
| R03 | Key Developer Absence | $0 | $3,200 | $8,000 | Freelancer cost covered within contingency reserve. |
| R05 | Audio Latency | $0 | $1,200 | $4,800 | EC2 tier upgrade absorbed within monthly AWS budget. |

Step 5 - Plan Risk Responses

| No. | Risk | Strategy | Response Plan | Contingency Plan | Fallback Plan | Residual Risk |
| --- | --- | --- | --- | --- | --- | --- |
| R01 | AWS API Access Delay | Mitigate | Escalate to AWS Activate support. Add second AI engineer. Extend working hours. | Use mock API for testing until real access granted. | Deploy without AI sessions; add as v1.1 post-launch (CR-001 raised). | Slight reduction in AI session quality with mock data. |
| R02 | AI Model Underperformance | Mitigate | Run model evaluation by Week 6. Source additional training data from open datasets. | Switch to a rule-based genre filter as fallback. | Launch without AI sessions; manual curation by admin until v1.1. | Reduced personalisation feature quality. |
| R03 | Key Developer Absence | Mitigate | Cross-train backend developers on AI integration tasks. Maintain up-to-date task documentation. | Redistribute tasks to available team members and extend working hours. | Hire a freelance developer from Upwork within 48 hours for critical-path tasks. | Slight quality risk if freelancer unfamiliar with codebase. |
| R04 | Scope Creep | Avoid | Hold formal scope review meeting with sponsor at kickoff. All requests must go through formal change request process. | Log request in change register and assess impact on cost and schedule before accepting. | Defer all out-of-scope features to v2.0 product roadmap. | Minor stakeholder dissatisfaction if features deferred. |
| R05 | Audio Streaming Latency > 3s | Mitigate | Implement CDN caching and audio compression during A11. Run load tests at 1,000 concurrent users. | Increase AWS EC2 instance tier temporarily to improve throughput. | Reduce initial audio quality to 128kbps on first load; upgrade quality after 3 seconds. | Marginal user experience impact during peak load. |
| R06 | Music Licensing Restrictions | Transfer | Engage legal counsel by Month 3 to finalise licensing agreements. Use royalty-free tracks as buffer. | Replace restricted tracks with licensed alternatives from a music API (e.g. Napster API). | Launch with 200,000 tracks and expand post-launch through phased licensing deals. | Smaller library at launch may affect user retention. |
| R07 | GDPR / Data Privacy Breach | Mitigate | Enforce HTTPS, bcrypt password hashing, and data encryption at rest from A05. Security audit after A09. | Patch identified vulnerabilities within 24 hours and notify affected users if breach occurs. | Temporarily suspend registration feature until security is confirmed. | Residual reputational risk even after resolution. |
| R08 | Inaccurate Duration Estimates | Mitigate | Use three-point PERT estimates for all tasks. Review estimates with tech lead before finalising. | Activate schedule reserve and re-sequence non-critical tasks to recover critical path. | Submit CR for revised go-live date (as done with CR-001 for A14). | Remaining activities may still carry estimation uncertainty. |
| R09 | Cloud Cost Overrun | Mitigate | Set AWS billing alerts at $450/month. Review and optimise S3 storage tiers monthly. | Switch to S3 Intelligent-Tiering to reduce storage costs automatically. | Draw from contingency reserve ($20,950) for overrun up to $5,000. | Minor budget impact absorbed within contingency. |
| R10 | Poor Test Coverage - Post-Launch Bugs | Mitigate | Define minimum 95% UAT pass rate gate before go-live. Allocate dedicated QA sprint with no feature additions. | Delay go-live by up to 5 days to address critical bugs before public launch. | Soft-launch to limited beta users (500) before full public release. | Minor non-critical bugs may still exist post-launch. |

Secondary Risks Introduced by Response Actions

| No. | Risk Responded To | Secondary Risk Introduced |
| --- | --- | --- |
| R01 | AWS API Delay | Second engineer added may slow other tasks due to onboarding time. |
| R02 | AI Underperformance | Additional training data sourcing may increase cloud storage cost by ~$500. |
| R03 | Key Developer Absence | Freelancer onboarding adds 2 days to any affected critical-path task. |
| R05 | Audio Latency | Upgrading EC2 instance tier costs an additional ~$1,200 per month. |
| R07 | GDPR Breach | Security patching may delay A09 (Profile Management Backend) by 1-2 days. |

Step 6 - Monitor Risks

6A. Risk Monitoring Approach

| Activity | Melodify Application |
| --- | --- |
| Bi-weekly Risk Register Review | PM reviews all open risks every 2 weeks. Updates probability, impact, status, and owner notes. New risks identified during development are added immediately. |
| Weekly SPI Monitoring | SPI calculated weekly from ProjectLibre data. If SPI falls below 0.85 for 2 consecutive weeks, all schedule-related risks are escalated from Medium to High. |
| Phase-End Risk Audit | External risk audit conducted at end of each project phase (Development, Testing, Deployment) to verify response plans were followed and assess residual risks. |
| Workaround Applied for R01 | AWS API delay exceeded planned contingency scope. PM implemented unplanned workaround: mock API for testing + Option B (third-party AI API) activated. Workaround cost: $4,000. |
| New Risk Identified at Week 11 | R11 (NEW): Third-party AI API rate limits lower than expected, causing session generation delays during peak usage. Rank: 3. Probability: Medium. Impact: Medium. Owner: AI Engineer. Response: Request higher rate-limit tier at $200/month additional cost. |

6B. Updated Risk Register Status - Week 11

| No. | Risk | Prev. Rank | Curr. Rank | Status | Latest Update |
| --- | --- | --- | --- | --- | --- |
| R01 | AWS API Delay | 1 | 1 | Open | Option B (third-party API) implemented. CR-001 approved. Go-live revised to 6 May 2026. |
| R02 | AI Underperformance | 3 | 2 | Open | Model now at 78% accuracy. Additional training data integrated. Target 85% by Week 14. |
| R11 (NEW) | Third-Party API Rate Limits | -- | 3 | New | Identified Week 11. Higher rate-limit tier requested. $200/month extra. Within contingency reserve. |
| R09 | Cloud Cost Overrun | 9 | -- | Closed | S3 Intelligent-Tiering resolved cost issue. Risk closed in Week 8. |

Risk Management Summary - Melodify

| Process | Melodify Outcome |
| --- | --- |
| Risk Attitude | Risk-averse. Fixed budget $270,000. Hard go-live 1 May 2026. Zero tolerance for overruns. Both negative and positive risks tracked. |
| 1. Plan | Risk budget: $60,500. Bi-weekly register reviews. Brainstorming + Delphi + SWOT. 4-category RBS defined. |
| 2. Identify | 10 risks identified across 4 RBS categories. SWOT analysis completed. Full risk register created. |
| 3. Qualitative | P/I matrix: R01 and R05 rated Critical/High. Top 10 Risk Tracking table updated at Week 10. |
| 4. Quantitative | EMV decision tree: Option B selected for R01 (EMV -$5,200 vs -$10,800). Sensitivity analysis covers top 4 cost risks. |
| 5. Respond | All 10 risks have response, contingency, fallback, and residual risk plans. Secondary risks documented. |
| 6. Monitor | R01 workaround activated. R11 (new) added at Week 11. R09 closed. Go-live revised to 6 May 2026 via CR-001. |