Melodify Music Player

Project Schedule Management Plan

Date: May 2026  |  Deadline: 1 May 2026  |  Budget: $270,000

Step 1 — Plan Schedule Management

| Component | Melodify Decision |
| --- | --- |
| Schedule Model Development | CPM (Critical Path Method) with PDM (Precedence Diagramming Method) implemented in ProjectLibre. |
| Scheduling Methodology | Gantt chart with PDM dependencies. Activities linked using Finish-to-Start (FS) relationships as the default dependency type. |
| Level of Accuracy & Units | ±1 day for standard tasks; ±2 days for complex tasks (AI integration, backend, testing). Unit: working days (1 day = 8 hours, 8:00 AM–5:00 PM). Milestones = 0 duration. |
| Control Thresholds | Corrective action triggered if any task or phase exceeds 10% of its planned duration. Critical path activities are monitored daily — any slip directly delays the 1 May 2026 go-live. |
| Rules of Performance Measurement | % Complete tracked weekly in ProjectLibre. SPI = EV ÷ PV calculated monthly. SPI < 1 triggers immediate review. |
| Reporting Formats | Weekly Gantt chart report and critical path report shared with sponsor Marwan Moussa every Monday morning. |
| Process Descriptions | Activities defined from WBS → sequenced using PDM → durations estimated by responsible developers → schedule built in ProjectLibre → controlled via weekly reviews and SPI monitoring. |

Step 2 — Define Activities

Activity List & Milestones

Activities marked ♦ are milestones with zero duration. All others have assigned durations in Step 4.

| ID | Activity Name | Description | Predecessor | Successor | Type |
| --- | --- | --- | --- | --- | --- |
| A01 | Stakeholder Meeting & Requirements Gathering | Meet stakeholders, capture and verify all requirements. | — | A02 | Activity |
| M01 | Requirements Approved ♦ | All requirements signed off by sponsor. | A01 | A02 | Milestone |
| A02 | Project Planning & Scoping | Produce scope baseline, charter, and project schedule. | M01 | A03 | Activity |
| A03 | Team & Resource Management | Define roles, assign resources, manage capacity. | A02 | A04 | Activity |
| A04 | Budget Tracking Setup | Initialise budget tracking sheet against $270,000 fixed budget. | A02 | A05 | Activity |
| A05 | Backend DB Schema — User Data | Design and implement DB schema for user storage. | A03 | A06,A07 | Activity |
| A06 | Develop Sign-up Page | Frontend + backend for new user registration flow. | A05 | A08 | Activity |
| A07 | Develop Login Page | Credential validation, failed login handling. | A05 | A08 | Activity |
| M02 | Authentication Module Complete ♦ | Sign-up and login fully functional. | A06,A07 | A08 | Milestone |
| A08 | Frontend Profiles — Admins & Users | Design and build profile UI for both user roles. | M02 | A09 | Activity |
| A09 | Profile Management Backend | Backend logic for viewing, editing, deleting profiles. | A08 | A10 | Activity |
| A10 | Music Player UI Controls | Implement pause, next, back buttons and player interface. | A09 | A11 | Activity |
| A11 | Backend Audio Optimisation | Optimise audio streaming so songs load in ≤3 seconds. | A10 | A12 | Activity |
| M03 | Music Player Functional ♦ | Playback controls and audio streaming working end-to-end. | A11 | A12 | Milestone |
| A12 | Lyrics Cards UI | Build UI cards for lyrics display and favourite highlighting. | M03 | A13 | Activity |
| A13 | Lyrics Sharing Mechanism | Develop functionality for users to share lyrics snippets. | A12 | A14 | Activity |
| A14 | AI Session Generator Integration | Integrate AI to generate time-based genre sessions. | A13 | A15 | Activity |
| M04 | AI Integration Complete ♦ | AI recommendations and lyrics features fully operational. | A14 | A15 | Milestone |
| A15 | Admin Dashboard UI | Design and implement admin dashboard interface. | M04 | A16 | Activity |
| A16 | Admin Backend — User/Artist/Album CRUD | Backend logic for admins to create, edit, delete content. | A15 | A17 | Activity |
| A17 | Test Planning & Case Development | Create test plan and define test cases for all features. | A16 | A18 | Activity |
| A18 | Unit & Integration Testing | Test individual components and module integration. | A17 | A19 | Activity |
| A19 | System & UAT | Full system test + user acceptance testing (95% pass rate). | A18 | A20 | Activity |
| A20 | Performance Testing | Validate songs load ≤3 sec, uptime ≥98%. | A19 | A21 | Activity |
| M05 | UAT Sign-Off ♦ | Sponsor confirms 95% UAT pass rate achieved. | A20 | A21 | Milestone |
| A21 | Production Environment Setup | Configure cloud servers and production environment. | M05 | A22 | Activity |
| A22 | Data Migration & Content Loading | Migrate data; load 500,000+ songs into production. | A21 | A23 | Activity |
| A23 | User Training & Documentation | Prepare user manual and platform documentation. | A22 | A24 | Activity |
| A24 | Go-Live & Post-Launch Support | Launch platform publicly; monitor and resolve issues. | A23 | — | Activity |
| M06 | System Go-Live ♦ | Melodify live and accessible to the public. | A24 | — | Milestone |

Step 3 — Sequence Activities

Dependency Table

| From | To | Dependency Type | Rel. | Reason |
| --- | --- | --- | --- | --- |
| A01 | A02 | Mandatory | FS | Requirements must be gathered before planning can begin. |
| A02 | A03 | Mandatory | FS | Project plan must exist before roles and resources can be assigned. |
| A02 | A04 | Mandatory | FS | Scope must be locked before budget tracking is initialised. |
| A03 | A05 | Mandatory | FS | Resources must be assigned before any development work starts. |
| A05 | A06 | Mandatory | FS | DB schema must exist before sign-up page can store user data. |
| A05 | A07 | Mandatory | FS | DB schema must exist before login can validate credentials. |
| A06 | M02 | Mandatory | FS | Both sign-up and login must complete before authentication milestone. |
| A07 | M02 | Mandatory | FS | Both sign-up and login must complete before authentication milestone. |
| M02 | A08 | Mandatory | FS | Auth module must be complete before profile pages are built. |
| A08 | A09 | Mandatory | FS | Frontend profile UI must exist before backend logic is wired. |
| A09 | A10 | Mandatory | FS | User data management must be in place before the music player is built. |
| A10 | A11 | Mandatory | FS | Player UI must exist before backend audio optimisation is tested. |
| A11 | A12 | Mandatory | FS | Audio streaming must be stable before lyrics features are layered on. |
| A12 | A13 | Discretionary | FS | Lyrics cards UI should be complete before sharing is built; could overlap. |
| A13 | A14 | Mandatory | FS | Sharing mechanism must work before AI session generator is integrated. |
| A14 | A15 | Discretionary | FS | AI integration should be done before admin dashboard, but admin can start in parallel if resources allow. |
| A15 | A16 | Mandatory | FS | Admin UI must exist before backend CRUD logic is connected. |
| A16 | A17 | Mandatory | FS | All features must be built before test planning and case development begins. |
| A17 | A18 | Mandatory | FS | Test cases must be defined before testing can begin. |
| A18 | A19 | Mandatory | FS | Unit tests must pass before full system and UAT can proceed. |
| A19 | A20 | Mandatory | FS | Functional correctness must be confirmed before performance is tested. |
| A20 | A21 | Mandatory | FS | All testing must pass before production environment is configured. |
| A21 | A22 | Mandatory | FS | Production environment must be ready before data migration starts. |
| A22 | A23 | Discretionary | FS | Documentation can start during data migration if team capacity allows. |
| A23 | A24 | Mandatory | FS | Documentation must be ready before go-live. |
| A05 | A11 | External | FS | Cloud storage provider (AWS S3) must confirm bucket access before audio optimisation can be completed. |
| A14 | A20 | External | FS | Third-party AI model API rate limit approval required before performance testing of session generation. |

| ■ White = Mandatory (Hard Logic) | ■ Blue = Discretionary (Soft Logic) | ■ Pink = External Dependency |
| --- | --- | --- |

Step 4 — Estimate Activity Durations

Duration = Effort (hrs) ÷ Resource Availability × (1 day / 8 hrs)

Three-point PERT estimate: Duration = (Optimistic + 4×Most Likely + Pessimistic) ÷ 6

| ID | Activity | Effort (hrs) | Resources | Optimistic (d) | Most Likely (d) | Pessimistic (d) | PERT (d) | Final Duration (d) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A01 | Stakeholder Meeting & Requirements Gathering | 50 | 1 | 5 | 7 | 10 | 7.2 | 7 |
| A02 | Project Planning & Scoping | 60 | 1 | 6 | 8 | 12 | 8.3 | 8 |
| A03 | Team & Resource Management | 70 | 1 | 7 | 9 | 14 | 9.5 | 10 |
| A04 | Budget Tracking Setup | 24 | 1 | 2 | 3 | 5 | 3.2 | 3 |
| A05 | Backend DB Schema — User Data | 40 | 1 | 4 | 5 | 8 | 5.3 | 5 |
| A06 | Develop Sign-up Page | 80 | 2 | 4 | 5 | 8 | 5.3 | 5 |
| A07 | Develop Login Page | 96 | 2 | 5 | 6 | 9 | 6.3 | 6 |
| A08 | Frontend Profiles — Admins & Users | 80 | 2 | 4 | 5 | 8 | 5.3 | 5 |
| A09 | Profile Management Backend | 80 | 2 | 4 | 5 | 8 | 5.3 | 5 |
| A10 | Music Player UI Controls | 160 | 2 | 8 | 10 | 15 | 10.5 | 11 |
| A11 | Backend Audio Optimisation | 120 | 2 | 6 | 8 | 12 | 8.3 | 8 |
| A12 | Lyrics Cards UI | 64 | 2 | 3 | 4 | 6 | 4.2 | 4 |
| A13 | Lyrics Sharing Mechanism | 72 | 2 | 4 | 5 | 7 | 5.2 | 5 |
| A14 | AI Session Generator Integration | 160 | 2 | 9 | 11 | 17 | 11.7 | 12 |
| A15 | Admin Dashboard UI | 80 | 2 | 4 | 5 | 8 | 5.3 | 5 |
| A16 | Admin Backend — User/Artist/Album CRUD | 48 | 2 | 2 | 3 | 5 | 3.2 | 3 |
| A17 | Test Planning & Case Development | 48 | 1 | 5 | 6 | 9 | 6.3 | 6 |
| A18 | Unit & Integration Testing | 64 | 2 | 3 | 4 | 6 | 4.2 | 4 |
| A19 | System & UAT | 56 | 2 | 3 | 4 | 6 | 4.2 | 4 |
| A20 | Performance Testing | 24 | 1 | 2 | 3 | 5 | 3.2 | 3 |
| A21 | Production Environment Setup | 24 | 1 | 2 | 3 | 5 | 3.2 | 3 |
| A22 | Data Migration & Content Loading | 56 | 2 | 3 | 4 | 6 | 4.2 | 4 |
| A23 | User Training & Documentation | 8 | 1 | 1 | 1 | 2 | 1.2 | 1 |
| A24 | Go-Live & Post-Launch Support | 8 | 1 | 1 | 1 | 2 | 1.2 | 1 |

Step 5 — Develop the Schedule

Critical Path Analysis

The critical path is the longest sequence of dependent activities. Any delay on the critical path delays the project end date. Total project duration: 111 working days (~22 weeks).

Critical path sequence: A01 → M01 → A02 → A03 → A05 → A07 → M02 → A08 → A09 → A10 → A11 → M03 → A14 → M04 → A15 → A16 → A17 → A18 → A19 → A20 → M05 → A21 → A22 → A24 → M06

| ID | Activity | ES | EF | LS | LF | Float | Dur (d) | Critical |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A01 | Stakeholder Meeting & Requirements | Day 1 | Day 8 | Day 1 | Day 8 | 0 | 7 | YES ✓ |
| M01 | Requirements Approved ♦ | Day 8 | Day 8 | Day 8 | Day 8 | 0 | 0 | YES ✓ |
| A02 | Project Planning & Scoping | Day 8 | Day 16 | Day 8 | Day 16 | 0 | 8 | YES ✓ |
| A03 | Team & Resource Management | Day 16 | Day 26 | Day 16 | Day 26 | 0 | 10 | YES ✓ |
| A04 | Budget Tracking Setup | Day 16 | Day 19 | Day 23 | Day 26 | 7 | 3 | No |
| A05 | Backend DB Schema | Day 26 | Day 31 | Day 26 | Day 31 | 0 | 5 | YES ✓ |
| A06 | Develop Sign-up Page | Day 31 | Day 36 | Day 32 | Day 37 | 1 | 5 | No |
| A07 | Develop Login Page | Day 31 | Day 37 | Day 31 | Day 37 | 0 | 6 | YES ✓ |
| M02 | Authentication Module Complete ♦ | Day 37 | Day 37 | Day 37 | Day 37 | 0 | 0 | YES ✓ |
| A08 | Frontend Profiles | Day 37 | Day 42 | Day 37 | Day 42 | 0 | 5 | YES ✓ |
| A09 | Profile Management Backend | Day 42 | Day 47 | Day 42 | Day 47 | 0 | 5 | YES ✓ |
| A10 | Music Player UI Controls | Day 47 | Day 58 | Day 47 | Day 58 | 0 | 11 | YES ✓ |
| A11 | Backend Audio Optimisation | Day 58 | Day 66 | Day 58 | Day 66 | 0 | 8 | YES ✓ |
| M03 | Music Player Functional ♦ | Day 66 | Day 66 | Day 66 | Day 66 | 0 | 0 | YES ✓ |
| A12 | Lyrics Cards UI | Day 66 | Day 70 | Day 68 | Day 72 | 2 | 4 | No |
| A13 | Lyrics Sharing Mechanism | Day 70 | Day 75 | Day 72 | Day 77 | 2 | 5 | No |
| A14 | AI Session Generator | Day 66 | Day 78 | Day 66 | Day 78 | 0 | 12 | YES ✓ |
| M04 | AI Integration Complete ♦ | Day 78 | Day 78 | Day 78 | Day 78 | 0 | 0 | YES ✓ |
| A15 | Admin Dashboard UI | Day 78 | Day 83 | Day 78 | Day 83 | 0 | 5 | YES ✓ |
| A16 | Admin Backend CRUD | Day 83 | Day 86 | Day 83 | Day 86 | 0 | 3 | YES ✓ |
| A17 | Test Planning & Case Development | Day 86 | Day 92 | Day 86 | Day 92 | 0 | 6 | YES ✓ |
| A18 | Unit & Integration Testing | Day 92 | Day 96 | Day 92 | Day 96 | 0 | 4 | YES ✓ |
| A19 | System & UAT | Day 96 | Day 100 | Day 96 | Day 100 | 0 | 4 | YES ✓ |
| A20 | Performance Testing | Day 100 | Day 103 | Day 100 | Day 103 | 0 | 3 | YES ✓ |
| M05 | UAT Sign-Off ♦ | Day 103 | Day 103 | Day 103 | Day 103 | 0 | 0 | YES ✓ |
| A21 | Production Environment Setup | Day 103 | Day 106 | Day 103 | Day 106 | 0 | 3 | YES ✓ |
| A22 | Data Migration & Content Loading | Day 106 | Day 110 | Day 106 | Day 110 | 0 | 4 | YES ✓ |
| A23 | User Training & Documentation | Day 106 | Day 107 | Day 109 | Day 110 | 3 | 1 | No |
| A24 | Go-Live & Post-Launch Support | Day 110 | Day 111 | Day 110 | Day 111 | 0 | 1 | YES ✓ |
| M06 | System Go-Live ♦ | Day 111 | Day 111 | Day 111 | Day 111 | 0 | 0 | YES ✓ |

Step 6 — Control the Schedule

6A. Weekly Status at Week 10 — Schedule Performance

At Week 10 (Day 70), AI Session Generator integration (A14) has overrun by 3 days due to a delay in third-party AWS API rate-limit approval — an external dependency. This exceeds the 10% control threshold (12 planned days × 10% = 1.2 days). The critical path is impacted.

| ID | Activity | Planned (d) | Actual (d) | Status | SPI | Action Taken / Impact |
| --- | --- | --- | --- | --- | --- | --- |
| A10 | Music Player UI Controls | 11 | 11 | Complete | 1.00 | None |
| A11 | Backend Audio Optimisation | 8 | 9 | Complete | 0.89 | Extra developer assigned; recovered 1 day. |
| A12 | Lyrics Cards UI | 4 | 4 | Complete | 1.00 | None |
| A13 | Lyrics Sharing Mechanism | 5 | 5 | Complete | 1.00 | None |
| A14 | AI Session Generator | 12 | 15 | In Progress | 0.80 | ⚠ 3-day overrun (25% > 10% threshold). AWS API access delayed. PM escalated to sponsor. Second AI engineer added. Critical path impacted by 3 days. |
| A15 | Admin Dashboard UI | 5 | 5 | Not Started | — | Start delayed by 3 days due to A14 overrun. |
| A16 | Admin Backend CRUD | 3 | 3 | Not Started | — | Rescheduled accordingly. |

6B. Corrective Actions Applied

- A14 (AI Session Generator): Second AI engineer assigned from Week 11. Working hours extended to 10-hour days for 3 days to recover the delay.

- Critical path updated in ProjectLibre: A15, A16, A17 start dates shifted by 3 days. New project end date: Day 114 (3 days after original 1 May 2026 deadline).

- Sponsor Marwan Moussa notified via revised critical path report on Monday of Week 11.

- A23 (User Training & Documentation) scope reduced to a 1-day digital guide only, freeing 0 critical-path days but reducing non-critical float to 0.

- PM requested formal change request CR-001 to extend go-live by 3 working days to 6 May 2026, approved by sponsor.

6C. Updated Critical Path After Corrective Action

| Item | Value |
| --- | --- |
| Original project end date | Day 111 (1 May 2026) |
| A14 overrun | +3 days (AWS API delay — External dependency) |
| Recovery action | Additional engineer + extended hours on A14 |
| Days recovered | 0 days (overrun absorbed into schedule — CR-001 raised) |
| Revised project end date | Day 114 (6 May 2026) — approved via CR-001 |