# Project Scope Plan & Baseline

Project Name: Melodify Music Player

Date Prepared: 4/3/2026

Prepared by: Nour Waleed, Hagar Aly, Ahmed khalid

## 1. Introduction

This document provides a brief overview of the Scope Baseline for the Melodify music player project. It serves as the formal definition of the project scope and will be used as a reference point for managing the project and controlling scope changes. This document includes the Project Scope Statement, the Work Breakdown Structure (WBS), and theWBS  Dictionary, which together define the entire scope of the project.

## 2. Project Scope Statement

### 2.1. Project Justification

This project aims to have a modern approach where music can be shared and  listened to online and end the DVDs and CDs era.

The current music player does not have music sessions where it is focused on a specific genre with a time base before having a pause. And they do not annotate or share lyrics, as they must share the whole song.

Our music player shall provide a place to annotate the lyrics they want and share it with their friends and family.

Expected Benefits:

-Focused on the emotional side where they share lyrics instead of a whole song.

-It shall improve teens' satisfaction by 85%, by providing more features like time based sessions player.

### 2.2. Product Scope Description

Our aim is to deliver a modern approach for how users listen to music. Firstly, our user will be able to create private music study/work sessions where they can lock in and focus on their work and it can be customized based on their mood. Secondly, they will be able to have an AI assistant anytime, where it can help them find a song, artist, or create a playlist based on what they are feeling. Thirdly, they can share snippets of lyrics with their friends - they don’t need to share the whole song if they are not feeling it, or annotate the lyrics they want and come back to it whenever they want.

### 2.3. Project Deliverables:

-       Functional Music Player Platform: A fully deployed and operational web application accessible to the public.

- Fully deployed web frontend: A functional UI/UX design featuring user profiles, lyrics, cards, and playback controls.

- AI generator: an integrated AI assistant model capable of helping  users to find favorite songs and creating time based genre sessions.

- analytics and admin dashboards: portals for music analytics and administrative management of users and content

-       Artist Portal: A secure area for artists to create, manage, and monitor their music profile.

-       User Portal: A a customizable dashboard for Users to access their playlists, track their listing journey, and manage their account however they like.

-       Tech team  Backend: A control panel for the tech team to manage users, artists, and platform settings.

### 2.4. Project Exclusions

- Normal user will not be able to publish any music, only the artist or authorized  publisher.

- podcast and radio live session

### 2.5. Constraints

- The project must be completed before 1st of May 2026.

- This project have fixed budget of 270,000.

- Unable to get the copyrights license..

| Constraint Category | Description |
| --- | --- |
| Schedule | The platform must be done and deployed by 1st of May 2026 |
| Budget | The fixed budget for this project development is $270,000 |
| License | Need to get the copyrights license for the songs that will be available on our website |

### 2.6. Assumptions:

- Users are assumed to understand standard playback symbols without specialized training

- Over 500,000 music ready to be deployed in Melodify before the deployment phase begins.

- the chosen cloud hosting environment is capable to support the goal of achieving 1,000,000 users after one year os deployment without requiring writing the backend again

- stakeholders availability: the primary sponsor, Marwan Moussa, will be available to review and approve the final report to meet closure criteria

### 2.7. Project Acceptance Criteria

-Songs must not take more than 3 seconds to load. System uptime must be equal or exceed 98%

- The payment gateway integration must process transactions securely and successfully with a success rate of at least 99.5%.

-  User Acceptance Testing (UAT) must be completed with a 95% pass rate on all critical and major test cases.

-The platform must pass a third-party security audit with no critical or high-severity vulnerabilities identified.

## 3. Work Breakdown Structure (WBS)

1 Melodify Music Player

1.0 Project Management

1.1 Task Distribution

1.1.1 Stakeholder Meeting & Requirements Gathering

1.1.2 Project Planning & Scoping

1.1.3 Team & Resource Management

1.1.4 Project Tracking & Stakeholder Reporting

1.1.5 Budget tracking

2.0  Platform and User Account Management

2.1 Authentication

2.1.1 Develop a signup page that registers users

2.1.2 Develop a login page that checks if the users are valid

2.2 Profile Design and Management

2.2.1 Implement frontend profiles for admins and users

2.2.2 Implement backend database schemas for user data storage

3.0 Music Player and Interactive lyrics

3.1 Music Player Controls

3.1.1 Implement pause, next and back button function

3.1.2 Optimize backend so that a song doesn’t take more than 5 seconds to load

3.2 Lyrics annotation and AI integration

3.2.1 Build the UI for lyrics cards and highlight the favourite picks

3.2.2 Develop the sharing mechanisms for lyrics

3.2.3 Integrate the AI and Program it to generate time-based sessions based on genre

4.0 Admin Controls

4.1 Administrative dashboard

4.1.1 Build the admin dashboard UI

4.1.2 Implement backend logic to create, edit and remove users, artists and albums

5.0 Testing & Publishing

5.1 Testing & Quality Assurance

5.1.1 Test Planning & Case Development

5.1.2 Unit & Integration Testing

5.1.3 System & User Acceptance Testing

5.1.4 Performance Testing

5.2  Deployment & Launch

5.2.1 Production Environment Setup & Configuration

5.2.2 Data Migration & Content Loading

5.2.3 User Training & Documentation

5.2.4 Go-Live & Post-Launch Support

## 4. WBS Dictionary

| WBS Code | Element Name | Description of Work | Deliverable(s) | Estimated Hours | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 1.1. | Task Distribution | Organize project tasks and assign responsibilities to team members | Task assignment document,WBS | 100 | All tasks clearly assigned to team members and documented |
| 1.1.1 | Stakeholder Meeting & Requirements Gathering | Meeting with the stakeholders and specify the project requirements. | Requirements document | 50 | All requirements known and verified by stakeholders |
| 1.1.2 | Project Planning & Scoping | Define project scope, timeline, and milestones | Project plan, gantt chart | 60 | Timeline and scope clearly defined and agreed by team |
| 1.1.3 | Team & Resource Management | Manage team roles, tools, and resources needed for development | Resource allocation plan | 70 | Roles and resources clearly documented and accessible to team |
| 1.1.4 | Project Tracking & Stakeholder Reporting | Track project progress and provide updates to stakeholders | Progress reports /status update | 120 | Regular progress reports delivered and project milestones tracked |
| 1.1.5 | Budget tracking | Monitor project expenses and manage resource usage | Budget tracking sheet | 300 | Budget records updated and within defined limits |
| 2.1 | Authentication | Design and implemented secure user authentication system | Authentication module | 70 | User can securely register, login, and access their accounts |
| 2.1.1 | Develop a signup page that registers users | Create a signup page that allows new users to register by entering their information | Functional User Sign up System | 100 | Users can successfully register and their data is stored in the database |
| 2.1.2 | Develop a login page that checks if the users are valid | Develop a login page that validates user credentials and allows secure access | Functional Login System | 120 | Registered users can login successfully using correct credentials |
| 2.2 | Profile Design and Management | Design and manage user profile for admins and regular | Profile management system | 90 | Profiled display correct user data and allow updates |
| 2.2.1 | Implement frontend profiles for admins and users | Developed the frontend interface for admin and user profiles | Profile UI page | 100 | Profile pages display correctly and allows user interaction |
| 2.2.2 | Implement backend database schemas for user data storage | Design and implemented database structure for storing user info | Database schema for users info | 40 | User data is stored, retrieved, and updated correctly in the database |
| 3.1 | Music Player Controls | Implement core controls for music playback | Functional music player | 200 | Music player can play, pause,, skip, and load song successfully |
| 3.1.1 | Implement pause, next and back button function | Implement pause, next, and previous buttons for the music player | Functional music control buttons | 200 | Users can pause, skip forward, and go back between songs correctly. |
| 3.1.2 | Optimize backend so that a song doesn’t take more than 5 seconds to load | Optimize backend performance so songs load quickly | Optimized audio loading system | 150 | Users can pause, skip forward, and go back between songs correctly |
| 3.2 | Lyrics annotation and snippets | Develop lyrics interface and integrate AI features | Lyrics annotation system with AI integration | 100 | Lyrics display correctly and AI generates sessions based on genre |
| 3.2.1 | Build the UI for lyrics cards and highlight the favourite picks | Design and implement UI cards for displaying song lyrics and highlighting favourites | Lyrics UI interface | 80 | Lyrics display correctly and favourite highlights work properly |
| 3.2.2 | Develop the sharing mechanisms for lyrics | Develop functionality that allows users to share lyrics with others | Lyrics sharing system | 90 | Users can share selected lyrics successfully |
| 3.2.3 | Integrate the AI and Program it to generate time-based sessions based on genre | Integrate AI to generate time-based music sessions based on selected genre | AI recommendation Module | 40 | AI generated playlist/sessions correctly based on genre input |
| 4.1 | Administrative dashboard | Build dashboard for admins to manage system content | Admin dashboard interface | 98 | Admin can manage users, artists, and albums successfully |
| 4.1.1 | Build the admin dashboard UI | Design and implement the user interface for the admin dashboard | Admin dashboard interface | 100 | Admin dashboard can displays correctly and allows navigation between admin features |
| 4.1.2 | Implement backend logic to create, edit and remove users, artists and albums | Develop backend logic that allows admins to create, edit, and delete users, artists, and albums | Admin management system | 60 | Admin can successfully manage users, artists,and albums from the dashboard |
| 5.1 | Testing & Quality Assurance | Perform testing to ensure system reliability and quality | Test cases and test reports | 50 | All major features tested with minimal critical bugs |
| 5.1.1 | Test Planning & Case Development | Create test plans and define test cases for all system features | Test plan document and test cases | 60 | Test cover all main system functions and scenarios |
| 5.1.2 | Unit & Integration Testing | Test individual components and verify integration between modules | Unit and integration test results | 80 | System modules work individually and together without major errors |
| 5.1.3 | System & User Acceptance Testing | Perform full system testing and validate functionality with users | UAT report | 70 | User confirm the system meets requirements and works as expected |
| 5.1.4 | Performance Testing | Test system speed, loading time, and overall performance | Performance test report | 30 | System performance meets required benchmarks |
| 5.2 | Deployment & Launch | Deploy the system and prepare it for real user | Live deployed system | 60 | System successfully deployed and accessible to users |
| 5.2.1 | Production Environment Setup & Configuration | Set up the production server and configure the system environment | Configured Production environment | 30 | System runs correctly in the production environment without configuration errors |
| 5.2.2 | Data Migration & Content Loading | Transfer necessary data and upload system content such as songs and lyrics | Migrated database and loaded content | 70 | All required data is successfully migrated and accessible in the system |
| 5.2.3 | User Training & Documentation | Prepare documentation and guide users on how to use the platform | User manual/ documentation | 5 | Documentation clearly explains system usage and features |
| 5.2.4 | Go-Live & Post-Launch Support | Launch the system for public use and monitor for issue after deployment | Live deployed platform and support report | 5 | System live, accessible to users, and critical issues are resolved quickly |

## 5. Approval and Sign-Off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Manager | Nour Waleed | Nour Waleed | 3/4/2026 |
| Project Sponsor | Marawan Mousa | Marawan Mousa | 3/4/2026 |